## Backlog
Issue Type | Summary | Description | Epic Link | Epic Name | Acceptance Criteria | Sprint | Why This Matters | Technical Implementation Notes
Epic | Foundations | Set up environment and build reusable tools. |  | Foundations |  |  | Enables all downstream work.
Epic | Build the populations | Find payment processes and controls. |  | Build the populations |  |  | Establishes scope.
Epic | Classification | Classify taxonomies using LLMs. |  | Classification |  |  | Enriches for analysis.
Epic | Bridge table | Assemble master analytical table. |  | Bridge table |  |  | Single source of truth.
Epic | Analytical outputs | Produce sponsor deliverables. |  | Analytical outputs |  |  | What you present.
Epic | Validation and audit | Validate LLM accuracy. |  | Validation and audit |  |  | Proves quality.
Story | Get LLM access working | Set up Claude and Gemini API access. | Foundations |  | 1. Can call both models 2. JSON responses work 3. Credentials secure | Sprint 1 | LLMs power all classification steps. Without this nothing works. | Setup: Claude Sonnet 4 and Gemini 1.5 Pro. Store keys in environment variables. Test with sample prompts. Rate limit 10 calls/sec. PRIMARY_MODEL=claude-sonnet-4, INDEPENDENT_MODEL=gemini-1.5-pro
Story | Check what's in JUNO | Load and profile JUNO controls from BIP1ViewA. | Foundations |  | 1. Loaded from BIP1ViewA.CONTROLS 2. Counts generated 3. Orphan keys under 5% 4. Go/no-go decision | Sprint 1 | Need to know control count and data quality before starting PoC. | Load: SELECT ctrl_id,ctrl_name,ctrl_description,risk_library_id,control_type,automation_level,overall_effectiveness FROM BIP1ViewA.CONTROLS WHERE status IN ('Active','Under Review'). Profile counts: total, 7.4.x tagged, with ratings, with process links. Orphan check: ctrl_id in linkage but not master. Go if orphans<5% AND ratings>60%
Story | Check what's in Holocentric | Load and profile Holocentric processes. L2 to L3 to Task hierarchy. | Foundations |  | 1. Loaded to SAS 2. L2/L3/Task counts 3. Task descriptions >80% 4. Linkage to JUNO checked | Sprint 1 | Need Task descriptions for Step 5 bespoke discovery. If <80% coverage LLM work fails. | HIERARCHY: L2 Process contains L3 Activities contains Tasks. Example: L2=Payments Processing to L3=BPAY Execution to Task=Supervisor approves batch. In Step 5 we scan TASK descriptions for control statements. Profile: count L2, L3, Tasks, Tasks with descriptions (need >80%). Check linkage to BIP1ViewA.linkage_ctrl_proc. Go if task descriptions >80%
Story | Check linkage tables | Load four linkage tables from BIP1ViewA. | Foundations |  | 1. All four loaded 2. Densities profiled 3. Join paths verified | Sprint 1 | Linkages enable convergence loop and Payment Nature inheritance. | Load from BIP1ViewA: CONTROL_PROCESS_LINK, CONTROL_OBLIGATION_LINK, CONTROL_INCIDENT_LINK, CONTROL_ISSUE_LINK. Also load OBLIGATIONS (NPP,BECS,RBA sources), INCIDENTS (severities), ISSUES (action_taken_text for Step 5c). Profile linkage density per table.
Story | Build the prompts | Write LLM prompts for Steps 2 | 3 | 5 | 7 | 8 | 9. | Foundations |  | 1. Prompts for 6 steps 2. JSON schemas defined 3. Confidence rubrics | Sprint 2 | Prompt quality directly impacts classification accuracy. | Prompt structure: System Context, Task, Input Format, Output JSON Schema, Confidence Rubric (High/Medium/Low), Examples. Store in 01_prompts/step0X_name.txt. Example Step 3 Payment Nature: 5 nature definitions (C to C HIGH risk, I to C HIGH, C to I MED, I to I MED, Supplier/Employee LOW), JSON output with applicable_natures array, confidence if explicit=High if inferable=Medium if ambiguous=Low
Story | Set up embeddings and compute for ALL | Compute embeddings for FULL Holocentric and JUNO universes. | Foundations |  | 1. Model selected 2. Batch processor built 3. ALL ~1200 Holocentric 4. ALL ~4500 JUNO 5. Saved to .npy files 6. Quality tested | Sprint 2 | Embeddings used 3+ times (PP6 | P6 | mechanism similarity). Compute once here reuse later. Do NOT recompute in Sprint 3. | CRITICAL: Compute FULL universes here. Sprint 3 will LOAD not recompute. Model: text-embedding-3-large (3072-dim). For Holocentric: concatenate L3 description + all Task descriptions. For JUNO: use ctrl_description. Save: 04_embeddings/holocentric_process_embeddings.npy + embedding_index_processes.csv. Save: 04_embeddings/control_embeddings.npy + embedding_index_controls.csv. Cost ~$0.12 total.
Story | Build fuzzy matching tool | Detect paraphrased duplicates for Step 5 bespoke discovery. | Foundations |  | 1. Fuzzy matcher built 2. Tested on 20 pairs 3. Threshold 0.80 calibrated 4. Tested on real bespokes | Sprint 2 | Step 5 extracts candidate controls from Tasks. Must check if already in JUNO under different wording. Without fuzzy match you flag existing controls as missing. | WHY NEEDED: Task says supervisor approves batch vs JUNO says manager batch approval - same control different words. Implementation: from rapidfuzz import fuzz; similarity = fuzz.token_set_ratio(text1,text2)/100. Function find_best_match(candidate,juno_df,threshold=0.80) returns best ctrl_id or None. Calibrate on 20 pairs: 10 same-reworded, 10 different. Target recall>95% FP<5%. Used in Step 5a Holocentric and 5c incident remediation.
Story | Find payment processes deterministic | Run PP1 hierarchy PP2 value stream PP3 application PP5 keyword. | Build the populations |  | 1. Four paths on full Holocentric 2. Register with paths fired 3. Every process logged 4. Count by path | Sprint 2 | Step 2 of 12-step methodology. First-pass population before embedding (PP6 Sprint 3) and convergence. | WHAT ARE PP1-PP6? Process Paths. PP1=hierarchy (under Payments L2), PP2=value stream (Request to Payment), PP3=application (uses payment apps), PP4=linked to High-conf control (convergence Sprint 3), PP5=keyword (payment terms), PP6=embedding similarity (Sprint 3). This story: PP1,PP2,PP3,PP5 only. PP4 NOT yet (convergence), PP6 NOT yet (embeddings). Confidence: High if 2+ paths with 1+ being PP1/PP2, Medium if 1 path PP1/PP2/PP3, Low if only PP5. Output: step02_payment_process_register.sas7bdat
Story | Find payment controls deterministic | Run P1 taxonomy P3 obligation P4 incident/issue P5 keyword. | Build the populations |  | 1. Four paths on full JUNO 2. Register with paths 3. Taxonomy hygiene finding 4. Every control logged | Sprint 2 | Step 4 of 12-step methodology. First-pass population before embedding (P6 Sprint 3) and convergence. | WHAT ARE P1-P6? Control Paths. P1=taxonomy (7.4.x), P2=linked to High-conf process (convergence Sprint 3), P3=obligation (NPP,BECS,RBA), P4=incident/issue, P5=keyword, P6=embedding (Sprint 3). This story: P1,P3,P4,P5 only. P2 NOT yet (convergence), P6 NOT yet (embeddings). From BIP1ViewA: P1=WHERE risk_library_id LIKE '7.4.%', P3=join CONTROL_OBLIGATION_LINK to OBLIGATIONS WHERE source IN payment regs, P4=join CONTROL_INCIDENT_LINK and CONTROL_ISSUE_LINK, P5=regex on ctrl_description. Taxonomy hygiene: what % found via non-P1 paths (if >40% tagging weak).
Story | Find payment processes embedding PP6 | LOAD precomputed embeddings and find similar to high-conf core. | Build the populations |  | 1. Embeddings LOADED from Sprint 2 2. High-conf core identified 3. Threshold calibrated 4. Candidates queued to SME | Sprint 3 | PP6 uses embedding similarity to find processes missed by deterministic. Loads embeddings computed in Sprint 2 (do NOT recompute). | CRITICAL: LOAD embeddings from 04_embeddings/holocentric_process_embeddings.npy (computed in Sprint 2). Do NOT recompute. High-conf core = processes with pp1_fired=1 OR pp2_fired=1 OR pp3_fired=1. Compute cosine similarity of all other processes to core (average to top-k=10 neighbors). Calibrate threshold using golden set. Candidates above threshold go to SME queue NOT auto-included. Avoids false positives.
Story | Find payment controls embedding P6 | LOAD precomputed embeddings and find similar to high-conf core. | Build the populations |  | 1. Embeddings LOADED from Sprint 2 2. Core identified 3. Enrichment signals 4. Candidates queued ordered by score | Sprint 3 | P6 uses embedding similarity to find controls missed by deterministic. Loads embeddings from Sprint 2. | CRITICAL: LOAD embeddings from 04_embeddings/control_embeddings.npy (computed Sprint 2). Do NOT recompute. High-conf core = controls with p1_fired=1 OR p3_fired=1. Compute similarity. Enrichment signals: (1) Owner clustering: if 80%+ of business unit controls included flag rest, (2) Process-adjacency: controls on same app as included. Combined score: 0.5*similarity + 0.3*owner_clustering + 0.2*process_adjacency. Queue ordered by score.
Story | Run the convergence loop | Iterate Steps 2 and 4 with PP4 and P2 paths until stable. | Build the populations |  | 1. Loop runs until no new High/Medium 2. Confidence ceiling enforced 3. Low doesn't propagate 4. Pass-by-pass log | Sprint 3 | Steps 2 and 4 have chicken-egg dependency. Processes need controls and controls need processes. Convergence resolves this. | WHAT ARE STEPS 2 AND 4? From 12-step methodology: Step 2=Find processes, Step 4=Find controls. WHAT ARE PP4 AND P2? PP4=Process Path 4 (process linked to High-conf control), P2=Control Path 2 (control linked to High-conf process). HOW IT WORKS: Pass 1: Steps 2,4 run with PP4/P2 disabled. Pass 2+: Step 2 fires PP4 (use BIP1ViewA.linkage_ctrl_proc to find processes linked to High-conf controls), Step 4 fires P2 (find controls linked to High-conf processes). Rules: (1) Only High/Medium fire PP4/P2, (2) Medium source cannot create High inherited (ceiling), (3) Low stays in SME queue. Converge when pass N and N+1 have identical High/Medium counts. Hard cap 5 passes. Output: convergence_log.csv with pass_number, new_processes, new_controls.
Story | Classify Payment Nature for processes | LLM classifies which of 5 Payment Natures apply. | Classification |  | 1. LLM on all processes 2. Output with confidence/rationale 3. Low-conf queued 4. Validation gate passes | Sprint 3 | Step 3 of methodology. Enriches processes with Payment Nature taxonomy needed for coverage heatmaps. | Prompt: step03_payment_nature_processes.txt. Five natures: (1) C to C HIGH risk (BPAY, P2P), (2) I to C HIGH (interest, refunds), (3) C to I MED (fees, loan payments), (4) I to I MED (interbank), (5) Supplier/Employee LOW (payroll). Input: process_id, process_name, process_description (L3 + Tasks concatenated), value_stream, applications. Output JSON: {applicable_natures:[{nature,confidence,rationale}], requires_sme}. Process can have multiple natures. Queue to SME if confidence=Low OR multi-nature with conflicting risk.
Story | Build golden set for process inclusion | SME labels 30 processes. Measure false-negative rate. | Validation and audit |  | 1. SME constructs 30-process set 2. Independent LLM verifies 3. Primary measured 4. Pass if FNR<10% | Sprint 3 | Validates Step 2 PP6 embedding accuracy before scaling. 30 items sufficient for statistical confidence on binary classification. | WHY 30 ITEMS: For binary classification (is payment process yes/no), 30 items gives 95% confidence interval of +/-18%. If sparse data (few edge cases), SME can construct synthetic examples or use historical PoC data. SME selects: 10 clear payment (BPAY, NPP settlements), 10 clear non-payment (HR, marketing), 10 edge (fraud monitoring touches payments but is it payment process?). SME labels with rationale. Independent LLM verifies, disagreements adjudicated. Primary runs on same 30. Metric: FNR = (SME said True but model said False) / (total SME True). Pass if FNR<10%. If fail, revise prompt.
Story | Find bespoke in Holocentric | LLM scans Task descriptions for control statements. | Build the populations |  | 1. LLM on all Tasks 2. Fuzzy-matched against JUNO 3. Unmatched to bespoke register 4. Audit trail | Sprint 4 | Step 5a of methodology. Finds controls operating in practice but not registered in JUNO. Scans Task level (most granular). | RECALL HIERARCHY: L2 Process to L3 Activity to Task. We scan TASK descriptions (most granular). For each process in payment process register, extract all Tasks. LLM prompt: Does this Task perform control function (approval, validation, reconciliation, monitoring, segregation, authorization)? JSON: {is_control:true/false, control_description, confidence}. If is_control=true: fuzzy-match control_description against all JUNO ctrl_description using fuzzy_matcher.py from Sprint 2. If fuzzy similarity<0.75, add to bespoke register: {bespoke_id, source_type=Holocentric-Task, source_process_id, source_task_id, control_description, confidence}.
Story | Find bespoke in incident/issue remediation | LLM extracts control statements from Issue Action and closure text. | Build the populations |  | 1. LLM on incident/issue remediation 2. Fuzzy-matched 3. Unmatched to register 4. Deduplicate within register | Sprint 4 | Step 5c. Finds controls introduced after failures. Uses Issue Action text and rectification/closure text. | Query payment incidents/issues from BIP1ViewA.INCIDENTS and BIP1ViewA.ISSUES. Extract: incident closure_text, issue action_taken_text, issue rectification_text. LLM prompt: Extract any control statements (new checks added, approvals introduced, monitoring established after failure). JSON: {controls_extracted:[{control_description,confidence}]}. For each extracted: fuzzy-match against JUNO. Unmatched to bespoke register with source_type=remediation. After Step 5a and 5c complete: deduplicate within bespoke register itself (fuzzy-match within register, merge near-duplicates).
Story | Build golden set for bespoke discovery | SME labels 40 items across Holocentric and remediation. Measure precision. | Validation and audit |  | 1. SME constructs 40-item set 2. Independent verifies 3. Primary measured 4. Pass if precision>75% | Sprint 4 | Validates Step 5 bespoke discovery accuracy. 40 items split: 20 Holocentric Tasks | 20 incident/issue texts. | WHY 40 ITEMS: Step 5 has two streams (Holocentric, remediation). Need coverage of both. 20 per stream sufficient. If sparse data: SME can use historical audit findings or create synthetic examples (reword known controls). SME selects: 20 Holocentric Tasks (10 are controls like supervisor approves batch, 10 not like send email notification), 20 remediation texts (10 contain control statements, 10 don't). SME labels: is_control=True/False with rationale. Independent LLM verifies. Primary runs on same 40. Metric: precision = (model said True AND SME said True) / (all model said True). Target precision>75% per stream. OK to miss real controls but low FP critical to avoid polluting bespoke register.
Story | Assign Payment Nature to controls inheritance | For controls linked to processes inherit Natures (UNION). | Classification |  | 1. Controls linked inherit (UNION) 2. Confidence=High 3. Output control-to-nature 4. Coverage expect 60-80% | Sprint 5 | Step 7a of methodology. Deterministic inheritance from processes to controls via linkage table. High confidence. | Join controls to processes via BIP1ViewA.linkage_ctrl_proc. For each control: Payment_Nature = UNION of all Payment_Natures from linked processes. Confidence = High (structural inheritance). SQL: SELECT c.ctrl_id, p.payment_nature FROM step04_payment_control_register c INNER JOIN linkage_ctrl_proc lnk ON c.ctrl_id=lnk.ctrl_id INNER JOIN step02_payment_process_register p ON lnk.bus_unit_bcrm_id=p.l3_activity_id. Control can have multiple natures if linked to processes with different natures. Output: step07_control_to_nature_inherited.sas7bdat. Coverage: what % of controls have process links (expect 60-80%; unlinked fall to LLM).
Story | Assign Payment Nature LLM fallback | For unlinked controls LLM classifies Nature. Confidence capped Medium. | Classification |  | 1. LLM on unlinked controls 2. Confidence capped Medium 3. Output appended 4. All queued to SME | Sprint 5 | Step 7b. For controls without process links LLM infers Nature from description. Less certain so capped at Medium. | Filter: WHERE ctrl_id NOT IN (step 7a inherited). LLM prompt: Classify Payment Nature from ctrl_description and context (obligation text, incident text if available). Input: ctrl_id, ctrl_description, obligation_text, incident_summary. Output JSON: {applicable_natures:[{nature,confidence,rationale}]}. Confidence ceiling: even if LLM says High, cap at Medium (no process link = structural uncertainty). Append to step07_control_to_nature_all.sas7bdat. Queue all to SME review (unlinked = lower confidence).
Story | Sanity check inherited Payment Natures | Sample 10% of inherited. LLM classifies blind. Compare. If disagree >15% halt. | Classification |  | 1. Sample 10% inherited 2. LLM classifies blind 3. Disagreement measured 4. Pass if <15% | Sprint 5 | Validates Step 7a inheritance quality. If disagreement high means either linkages wrong or Step 3 classifications wrong. | Stratified sample: 10% of controls with inherited Payment Nature (stratify by nature, control_type, business_unit). LLM classifies sample using same prompt as Step 7b fallback WITHOUT seeing inherited result. Compare: disagreement = LLM primary nature differs from inherited primary nature. Disagreement rate = disagreements / sample_size. Pass if <15%. If >=15%: indicates (1) process linkages incorrect, or (2) Step 3 process classifications wrong. Halt and re-validate Step 3 golden set. Output: step07_sanity_check_results.csv.
Story | Build golden set for Payment Nature on processes | SME labels 30 processes. Measure precision and recall per nature. | Validation and audit |  | 1. SME constructs 30-process set 2. Independent verifies 3. Primary measured per nature 4. Pass if precision>85% AND recall>80% | Sprint 5 | Validates Step 3 Payment Nature classification accuracy. 30 items sufficient for multi-class with 5 categories. | WHY 30 ITEMS: 5 natures, need 6 examples per nature minimum. 30 gives 95% CI of +/-18% per nature. If sparse data: SME can construct edge cases synthetically. SME selects: 10 single-nature (clear C to C only, clear I to C only), 10 multi-nature (process spans C to C AND C to I), 10 ambiguous (borderline). SME labels: applicable_natures per process with rationale. Independent LLM verifies. Primary runs on same 30. Metrics PER NATURE: Precision(CTx) = (model assigned CTx AND SME assigned CTx) / (model assigned CTx). Recall(CTx) = same numerator / (SME assigned CTx). Pass if ALL five natures meet precision>85% AND recall>80%.
Story | Map controls to Master Controls CT1-CT28 | LLM maps each control to 1+ CTs. Cite rationale from description. | Classification |  | 1. LLM on all controls 2. Output with cited rationale 3. Rationale grounding enforced 4. Low-conf and Governance queued | Sprint 6 | Step 8 of methodology. Maps controls to CT outcomes. Biggest LLM workload (3000-6000 calls). Rationale grounding critical. | Prompt: step08_ct_mapping.txt. Input: ctrl_id, ctrl_description, control_type, automation_level. Output JSON: {ct_outcomes:[{ct:CT1,rationale_quote:phrase from description}], control_category:Process/System/ThirdParty/Pervasive, control_nature:Preventative/Detective/Corrective, framework_alignment:Payments/Governance}. RATIONALE GROUNDING: response must cite specific phrases from ctrl_description. No citations = API call fails, retry. Queue to SME: confidence=Low OR (framework_alignment=Governance AND taxonomy_tag=7.4.x) - these are misclassified. Audit: audit_trail_step08.csv. Biggest workload: 3000-6000 API calls.
Story | Place controls in lifecycle stages | LLM assigns stage A-G. Compare to structural where available. | Classification |  | 1. Structural placement where possible 2. LLM places all 3. Compare disagree=misplacement 4. Misplacement only where structural exists | Sprint 6 | Step 9. Assigns controls to payment lifecycle stages A Initiation through G Returns. | Structural placement: For controls linked to Holocentric steps parse step labels (Initiate, Authorize, Post, Reconcile, Report). Map to stages: A=Initiation, B=Validation, C=Authorization, D=Transmission, E=Posting, F=Reporting, G=Returns. Expect 30-60% have structural signal. LLM places all controls: lifecycle_stage:A/B/C/D/E/F/G. Can combine with Step 8 in single prompt. Compare: where both structural and LLM exist, if differ flag as potential misplacement (control in wrong stage). Output: step09_lifecycle_placement.sas7bdat with structural_stage, llm_stage, misplacement_flag.
Story | Build the bridge table | Join all outputs into master analytical table. Index on 5 dimensions. | Bridge table |  | 1. Bridge built from all upstream 2. Indexes on 5 dims 3. Row count reconciliation 4. Schema documented | Sprint 6 | Step 10. Single source of truth. Every Step 11 output queries this table. | SQL: SELECT c.ctrl_id, c.ctrl_name, c.control_category, c.automation_level, c.overall_effectiveness, ct.ct_outcome, n.payment_nature, lc.lifecycle_stage, p.l3_activity_id AS process_id, p.process_name, p.value_stream, lnk.linkage_type, inc.incident_count FROM step04_payment_control_register c LEFT JOIN step08_ct_mapping ct ON c.ctrl_id=ct.ctrl_id LEFT JOIN step07_control_to_nature_all n ON c.ctrl_id=n.ctrl_id LEFT JOIN step09_lifecycle_placement lc ON c.ctrl_id=lc.ctrl_id LEFT JOIN BIP1ViewA.linkage_ctrl_proc lnk ON c.ctrl_id=lnk.ctrl_id LEFT JOIN step02_payment_process_register p ON lnk.bus_unit_bcrm_id=p.l3_activity_id LEFT JOIN incidents_summary inc ON c.ctrl_id=inc.ctrl_id. Indexes: ct_outcome, payment_nature, lifecycle_stage, control_category, value_stream. Reconciliation: sum(CTs per control * Natures per control) = bridge row count.
Story | Build review queue | Queue for Low-conf and primary/independent disagreements. Prioritize by risk. | Validation and audit |  | 1. Queue schema created 2. All LLM steps populate 3. Queryable by filters 4. SME resolution workflow | Sprint 6 | Step 12 review queue. Where LLMs uncertain or disagree SMEs adjudicate. | Queue table: item_id, source_step (2/3/5/7/8/9), item_description, primary_result, independent_result, disagreement_type (Low-confidence/Disagreement), nature_risk (High/Med/Low), ct_criticality (P0/P1/P2), priority_score, assigned_sme, status (Pending/Reviewed), sme_decision (Approve Primary/Approve Independent/Revise Custom/Reject), sme_rationale, resolution_date. Populate: if confidence=Low OR primary!=independent INSERT INTO queue. Priority: (nature_risk weight*3) + (ct_criticality weight*2). SME workflow: Excel 06_sme_review/sme_queue_combined.xlsx with dropdowns. Resolution propagates via queue_resolver.py updating source datasets.
Story | Build golden set for CT mapping | SME labels 50 controls covering all 28 CTs. Measure CT-level precision/recall. | Validation and audit |  | 1. SME constructs 50-control set 2. SME assigns CTs with rationale 3. Independent verifies 4. Pass if avg precision>85% AND recall>80% | Sprint 6 | Validates Step 8 CT mapping accuracy. 50 items ensures all 28 CTs covered. | WHY 50 ITEMS: 28 CTs, need ~2 examples per CT minimum. 50 ensures coverage with extras for common CTs. If sparse: SME can reuse controls from other golden sets or create synthetic. Stratified sample: 50 controls ensuring every CT appears at least once (some CTs have 3-4 controls, rare CTs have 1). Mix: automated/manual, key/non-key, JUNO/bespoke. SME assigns: ct_outcomes per control (1-N CTs) with rationale grounded in ctrl_description. Independent LLM verifies. Primary runs on same 50. Metrics PER CT: Precision(CTx)=(model assigned CTx AND SME assigned CTx)/(model assigned CTx). Recall(CTx)=same/(SME assigned CTx). Pass if average across 28 CTs: precision>85% AND recall>80%.
Story | Build golden set for lifecycle | Reuse 50 controls from CT golden set. SME adds stage. Measure exact-match. | Validation and audit |  | 1. Reuse 50 from CT set 2. SME adds stage 3. Independent verifies 4. Pass if exact-match>80% | Sprint 6 | Validates Step 9 lifecycle placement. Reuses CT golden set controls (already stratified). | WHY 50 AND REUSE: Already have stratified 50-control set from Step 8. Reusing avoids SME burden. SME adds: lifecycle_stage (A-G) with rationale. Independent LLM verifies. Primary runs on same 50. Metric: exact-match accuracy = (model assigned correct stage) / 50. Pass if >=40 out of 50 correct (80%). Easier than CT mapping because only 7 choices not 28.
Story | Produce coverage heatmaps | Query bridge for Nature by CT | Value Stream by CT | Process by CT. Color code. | Analytical outputs |  | 1. Three heatmaps produced 2. Each cell shows Structural/Effective/Failing 3. Excel with color coding | Sprint 7 | Step 11a. Answers sponsor question: Where are we covered? Green=good | amber=moderate | red=gap. | WHY: Sponsor asks Do we have controls for C to C payments CT15 Sanctions Screening? Heatmap answers instantly. Three cuts: (1) Payment Nature by CT (5x28), (2) Value Stream by CT (8-12x28), (3) Process by CT (200-500x28). Each cell: Structural coverage (control exists), Effective coverage (rated Effective), Failing coverage (Effective but has incidents). SQL: SELECT payment_nature, ct_outcome, SUM(CASE WHEN ctrl_id IS NOT NULL THEN 1 END) AS structural, SUM(CASE WHEN overall_effectiveness IN ('Effective','Largely Effective') THEN 1 END) AS effective, SUM(CASE WHEN overall_effectiveness IN ('Effective','Largely Effective') AND incident_count>0 THEN 1 END) AS failing FROM bridge GROUP BY payment_nature, ct_outcome. Export to Excel with conditional formatting: GREEN if Effective>3 AND Failing=0, AMBER if Effective 1-2 OR Failing>0, RED if Structural=0.
Story | Produce strengthen view | Highlight automated in High-risk Natures | preventative at early stages | exemplars. | Analytical outputs |  | 1. Automated in High-risk 2. Preventative at A/B/C 3. Exemplars (Effective + no incidents) 4. Output consolidated | Sprint 7 | Step 11b. Showcases your BEST controls to auditor/regulator. Demonstrates strength of control environment. | WHY: Auditor visit - need to showcase best controls. This filters to: (1) Automated controls in High-risk Payment Natures (C to C, I to C), (2) Preventative controls at critical lifecycle stages (A Initiation, B Validation, C Authorization), (3) Exemplar candidates (Effective rating + zero incidents in 24 months). Three queries UNION ALL with subset_type field. Export to 11b_strengthen_view.xlsx with tabs per subset. Demonstrates control environment maturity.
Story | Produce governance misclassified | Filter framework=Governance with taxonomy 7.4.x. These belong elsewhere. | Analytical outputs |  | 1. Filter Governance + 7.4.x 2. Include rationale from Step 8 3. Output for risk owner review | Sprint 7 | Step 11d. Finds controls wrongly tagged Payments. They govern the framework not payment transactions. | SQL: SELECT c.ctrl_id, c.ctrl_name, c.ctrl_description, c.owner_business_unit, c.risk_library_id AS current_tag, ct.framework_alignment, ct.framework_rationale FROM bridge b INNER JOIN step08_ct_mapping ct ON b.ctrl_id=ct.ctrl_id WHERE ct.framework_alignment='Governance' AND c.risk_library_id LIKE '7.4.%'. Add recommendation='Remove from 7.4.x, re-home under Governance Risk'. Examples: committee oversight, policy authorship, training delivery. Export to 11d_governance_misclassified.xlsx.
Story | Build mechanism similarity calculator | Compute similarity between two controls using embeddings + automation + type. | Analytical outputs |  | 1. Function built 2. Uses embeddings + automation + type 3. Tested on duplicates and non-duplicates 4. Code documented | Sprint 7 | Used in Sprint 8 for duplicate detection. Detects if two controls work the same way. | Function: compute_mechanism_similarity(ctrl_A, ctrl_B, embeddings_dict). (1) Get description embeddings (3072-dim), (2) Encode automation: Automated=[1,0,0], Hybrid=[0,1,0], Manual=[0,0,1], (3) Encode control_type: Preventative=[1,0,0], Detective=[0,1,0], Corrective=[0,0,1], (4) Concatenate combined_A=[embedding_A, auto_A, type_A] (3078-dim), (5) Cosine similarity. CRITICAL RULE: if automation differs NOT duplicate even if similarity>=0.75 (defense-in-depth). Test: same control reworded >0.90, automated vs manual for same CT <0.70. File: mechanism_similarity.py
Story | Produce duplicate clusters and best-of-breed | Cluster by CT/Nature/Stage with similarity>0.75. Score. Highest=best-of-breed. | Analytical outputs |  | 1. Clusters identified 2. Each scored on 5 factors 3. Best-of-breed flagged 4. Retire/merge candidates | Sprint 8 | Step 11c. Consolidates duplicate controls. Identifies which to keep (best-of-breed) which to retire. | Cluster by (ct_outcome, payment_nature, lifecycle_stage, process_scope). Within cluster: pairwise mechanism similarity using mechanism_similarity.py from Sprint 7. If similarity>=0.75 AND automation matches = duplicate. Score each: 0.40*effectiveness (Effective=3, Largely=2, Req Impr=1, Ineffective=0) + 0.25*automation (Automated=3, Hybrid=2, Manual=1) + 0.20*incident_free (no incidents 24mo=1) + 0.10*design_clarity (description>50 words AND readable=1) + 0.05*coverage_breadth (linked to 3+ processes=1). Highest score = best-of-breed. Output: 11c_duplicates_best_of_breed.xlsx with cluster_id, controls, scores, best-of-breed flag, recommendation (retire/merge others).
Story | Produce gap register six types | Detect A no coverage | B insufficient | C unverified | D failing | E misplacement | F process gap. | Analytical outputs |  | 1. Six gap types extracted 2. Priority P0/P1/P2 3. Consolidated register 4. Export | Sprint 8 | Step 11e. Identifies coverage holes. Ranked by risk and criticality so you fix highest priority first. | Type A (no coverage): Generate all (Nature x CT) combos (5x28=140), left join to bridge, WHERE control_count=0. Type B (insufficient): GROUP BY (Nature,CT), HAVING all controls rated Req Improvement or Ineffective. Type C (unverified): WHERE overall_effectiveness IS NULL. Type D (failing): WHERE overall_effectiveness IN ('Effective','Largely Effective') AND incident_count>0 in 12mo. Type E (misplacement): WHERE structural_stage != llm_stage. Type F (process gap): processes with no linked controls. UNION ALL with gap_type field. Priority: P0 if nature_risk=High AND ct_criticality=P0, P1 if (High AND P1) OR (Medium AND P0), else P2. Export to 11e_gap_register_consolidated.xlsx with tab per type.
Story | Produce JUNO registration backlog | Extract SME-confirmed bespoke controls. Enrich. Rank by priority. | Analytical outputs |  | 1. Filter bespoke to SME-confirmed 2. Enrich with CT/Nature/Stage 3. Priority ranked 4. Output with full schema | Sprint 8 | Step 11f. Post-PoC to-do list for registering missing controls in JUNO. | SQL: SELECT b.bespoke_id, b.source_type (Holocentric-Task, remediation), b.control_description, b.source_process_id, ct.ct_outcome, n.payment_nature, lc.lifecycle_stage, p.applications, sme.sme_decision FROM step05_bespoke_register b LEFT JOIN sme_queue_resolution sme ON b.bespoke_id=sme.item_id WHERE sme.sme_decision IN ('Approve Primary','Approve Independent','Revise Custom') LEFT JOIN step08_ct_mapping ct ON b.bespoke_id=ct.ctrl_id LEFT JOIN step07_control_to_nature_all n ON b.bespoke_id=n.ctrl_id LEFT JOIN step09_lifecycle_placement lc ON b.bespoke_id=lc.ctrl_id LEFT JOIN step02_payment_process_register p ON b.source_process_id=p.l3_activity_id. Add priority (same logic as gap register). Recommended owner: inherit from source process owner. Export to 11g_juno_registration_backlog.xlsx.
Story | Produce monitoring baseline | Per CT: identify key controls | recommend monitoring intensity | list evidence vs gaps. | Analytical outputs |  | 1. Baseline per CT 2. Intensity scored (Low/Med/High/Critical) 3. Evidence vs gaps 4. Export | Sprint 8 | Step 11h. Post-PoC monitoring plan. Tells you which controls need monthly testing vs annual. Which are critical vs low priority. | WHY: Post-PoC someone monitors 3000+ controls. Which need monthly testing vs annual? Which critical vs low? Per CT: Query bridge ORDER BY best_of_breed_score DESC LIMIT 5 = key controls. Monitoring intensity: CASE WHEN nature_risk=High AND incident_count_24mo>5 THEN Critical WHEN nature_risk=High OR incident_count_24mo>2 THEN High WHEN nature_risk=Medium THEN Medium ELSE Low END. Existing evidence: join to monitoring log via ctrl_id, check latest_assessment_date. Gaps: WHERE monitoring_evidence=0 OR latest_assessment_date<CURRENT_DATE-365. Export to 11h_monitoring_baseline.xlsx with tab per CT showing key controls, intensity, evidence, gaps.
Story | PoC retrospective and reusability | Document generic backbone vs Payments overlay. Estimate effort for second risk class. | Validation and audit |  | 1. Backbone vs overlay separated 2. Effort estimate for second risk class 3. Lessons learned consolidated | Sprint 9 | Captures what's reusable for future PoCs in other risk domains. | Reusable backbone: (1) 12-step methodology structure, (2) Deterministic + embedding + convergence pattern, (3) Bridge table architecture (process,control,outcome,nature,stage), (4) Validation framework (golden sets, SME queues, independent LLM, audit trail), (5) Confidence rollup formulas, (6) Gap detection taxonomy. Payments overlay: (1) CT1-CT28 definitions, (2) 5 Payment Natures, (3) Lifecycle stages A-G, (4) Payment keywords/value streams. Effort for second risk class (Operational, Credit): expect 20-30% faster because backbone proven; only define new outcome taxonomy and nature taxonomy. Lessons learned: what prompts worked, what validation caught, where SME time bottlenecked, where LLM struggled. Output: 00_documentation/reusability_handover.docx