## Backlog
Issue Type | Summary | Description | Epic Link | Epic Name | Acceptance Criteria | Sprint | Technical Implementation Notes
Epic | Foundations | Set up environment, load all data sources (JUNO, Holocentric, ALEX, Alfabet, linkages), profile them, and build reusable tools (LLM access, prompts, audit trail, embeddings). |  | Foundations
Epic | Build the populations | Find payment processes (step 2), payment controls (step 4), bespoke controls (step 5), then run convergence loop (step 6) until populations stabilize. |  | Build the populations
Epic | Classification | LLM-classify Payment Nature on processes (step 3), Payment Nature on controls (step 7), Master Controls CT1-CT28 (step 8), and lifecycle stages A-G (step 9). |  | Classification
Epic | Bridge table | Assemble the master bridge table (step 10) combining processes, controls, CT outcomes, Payment Natures, lifecycle stages, ratings, and linkages. |  | Bridge table
Epic | Analytical outputs | Query bridge table to produce eight outputs (step 11): coverage heatmaps, strengthen view, duplicates/best-of-breed, governance misclassified, gap register, registration backlog, obligations coverage, monitoring baseline. |  | Analytical outputs
Epic | Validation and audit | SME-led validation with golden sets, independent LLM cross-checks, review queues for Low-confidence cases, and full audit trail (step 12). |  | Validation and audit
Story | Get LLM access working | Set up access to two LLM models from analytics environment. Test structured JSON responses. Store credentials securely. | Foundations |  | 1. Can call two different LLM families 2. Test prompt returns valid JSON 3. Credentials in env variables 4. Rate limiting works | Sprint 1 | Setup: Provision Claude Sonnet 4 and Gemini 1.5 Pro API keys. Install: pip install anthropic google-generativeai. Test script: call both models with test prompt, verify JSON response. Rate limiting: tenacity library, max 10 calls/sec. Config file: PRIMARY_MODEL and INDEPENDENT_MODEL constants. File: 02_code/python/llm_orchestration/test_llm_access.py
Story | Check what's in JUNO | Load JUNO controls and profile: total count, Payments-tagged (7.4.x), effectiveness ratings, process links. Check for orphan keys. | Foundations |  | 1. JUNO loaded to SAS staging 2. Counts: total, Payments-tagged, rated, linked 3. Orphan keys under 5% 4. Go/no-go decision | Sprint 1 | Teradata SQL: SELECT ctrl_id, ctrl_name, ctrl_description, risk_library_id, control_type, automation_level, overall_effectiveness FROM JUNO.CONTROLS WHERE status IN ('Active', 'Under Review'). SAS passthrough via proc sql. Profile: count total, sum(case when risk_library_id like '7.4.%'), sum(case when overall_effectiveness is not null). Orphan check: ctrl_id in linkage but not in master. Output: 00_documentation/juno_profile_report.html. Go if orphans < 5% AND ratings > 60%.
Story | Check what's in Holocentric | Load Holocentric processes. Check: L2/L3 counts, description coverage (need >80% for LLM), linkage to JUNO controls. | Foundations |  | 1. Holocentric loaded to SAS 2. L2/L3 counts, description coverage 3. Linkage to JUNO (expect 40-70%) 4. Go/no-go decision | Sprint 1 | Load CSV: proc import datafile='03_data/raw/holocentric_processes_YYYYMMDD.csv' dbms=csv. Profile: count L2 processes, L3 activities, descriptions not null (need > 80%), linkage to JUNO via bus_unit_bcrm_id. Output: 00_documentation/holocentric_profile_report.html. Go if descriptions > 80% AND linkage > 40%.
Story | Check linkage tables and obligations | Load four linkage tables (Control-Process, Control-Obligation, Control-Incident, Control-Issue) plus master tables. Profile densities and coverage. | Foundations |  | 1. All four linkages loaded 2. Density counts per table 3. Incident severities, obligation sources profiled 4. Join paths verified | Sprint 1 | Teradata SQL for each: Control_Process_Link, Control_Obligation_Link, Control_Incident_Link, Control_Issue_Link. Also load Obligations (NPP, BECS, RBA sources), Incidents (severity P1/P2/P3), Issues (priority). Profile: how many controls have links to each entity type. Output: 00_documentation/linkage_profile_report.html.
Story | Check what's in ALEX and Alfabet | Load ALEX (controls to applications) and Alfabet (application master). Check coverage. If low, flag impact on step 5b. | Foundations |  | 1. ALEX/Alfabet loaded or gap documented 2. JUNO coverage in ALEX (expect 40-80%) 3. Payment-relevant app list 4. Step 5b impact assessed | Sprint 1 | Load CSVs: alex_extract_YYYYMMDD.csv, alfabet_applications_YYYYMMDD.csv. Profile: how many JUNO controls appear in ALEX (expect 40-80%). Extract payment-relevant apps: apps used by payment processes OR linked to 7.4.x controls. If ALEX coverage < 20%, defer step 5b (ALEX bespoke discovery stream). ALEX provides Control_ID to Application_ID linkage, Data_Usage field (parse process IDs via regex), and CDE context.
Story | Build the schema dictionary | Consolidate all profiling into one Excel file: every field, data type, null rate, example values, usage in steps. | Foundations |  | 1. Schema dictionary Excel created 2. All sources documented (JUNO, Holocentric, ALEX, linkages) 3. Data quality findings noted 4. Lead engineer sign-off | Sprint 1 | Generate schema: proc contents on all staging datasets. Calculate null rates per field. Export to Excel (00_documentation/schema_dictionary.xlsx) with sheets per source. Columns: Field_Name, Data_Type, Null_Rate_Percent, Example_Values, Used_In_Steps. Add sheet for data quality findings (high null rates, orphan keys, missing sources).
Story | Onboard SMEs and brief them | Identify 2-3 SMEs from Line 1 Risk & Compliance. Brief on golden set construction, review queue workflow, time commitment. | Validation and audit |  | 1. 2-3 SMEs identified and onboarded 2. Briefing completed 3. Time commitment confirmed (2-4 hrs/wk Sprints 1-3, 4-8 hrs/wk Sprints 4-8) 4. Primary and backup designated | Sprint 1 | Coordinate with Line 1 leadership to nominate SMEs with Payments Risk expertise (NPP, BECS, RBA). Briefing agenda: (1) PoC overview, (2) SME role as ground truth, (3) Golden set construction per step, (4) Review queue workflow (Excel interface), (5) Time commitment breakdown. Document in 00_documentation/sme_engagement_plan.md with names, roles, availability, escalation path.
Story | Build the prompt library | Write LLM prompts for steps 2, 3, 5a/b/c, 7b/c, 8, 9. Each has: task, input format, JSON schema, confidence rubric. Version-control with SHA hashes. | Foundations |  | 1. Prompts written for 6 LLM steps 2. JSON schemas defined 3. Prompt versioning with SHA hashes 4. Changes trigger re-validation flag | Sprint 2 | Prompt template: System Context (definitions), Task, Input Format, Output Format (JSON schema), Confidence Rubric (High/Medium/Low criteria), Examples. Store in 01_prompts/step0X_[name].txt. Compute SHA-256 hash per file. Track in 01_prompts/prompt_versions.json. Example Step 3 Payment Nature prompt includes 5 nature definitions (C to C, I to C, C to I, I to I, Supplier/Employee), JSON schema with applicable_natures array, confidence rubric based on explicitness. Any prompt change sets validation_status='Pending', blocks production until re-validated.
Story | Build the audit trail framework | Create system to log every LLM call: prompt hash, model ID, timestamp, input hash, raw response, parsed result. | Foundations |  | 1. Audit trail table schema created 2. Test LLM call writes complete audit record 3. Re-run test: reproduce exact call from audit record 4. All LLM scripts include logging | Sprint 2 | Audit trail table fields: prompt_hash (SHA-256), model_id, run_timestamp, input_hash (SHA-256 of concatenated input fields), raw_response (full JSON), parsed_result (extracted fields), confidence, pass_number (for convergence loop). Implement as 05_audit_trail/audit_trail_step0X.csv per step. Python function: log_llm_call(step_id, prompt_hash, input_data, raw_response, parsed_result). Reproduce test: given audit record, reconstruct exact API call and verify same result.
Story | Set up embedding infrastructure | Choose embedding model (text-embedding-3-large). Build batch processor. Test on 100 processes and 100 controls. Save to numpy files. | Foundations |  | 1. Embedding model selected and tested 2. Batch processor with rate limiting 3. Embeddings saved to .npy files with CSV index 4. 200 items processed in < 30 seconds | Sprint 2 | Model: text-embedding-3-large (3072 dimensions) or ada-002 (1536 dimensions). Batch processor: chunk inputs to 100 per batch, handle rate limits via tenacity retry. Save: 04_embeddings/holocentric_process_embeddings.npy (numpy array), 04_embeddings/embedding_index_processes.csv (row_index, l3_activity_id mapping). Same for controls. Test on 200 items, verify under 30 sec. Reuse embeddings in steps 2 (PP6), 4 (P6), 11c (mechanism similarity).
Story | Build fuzzy matching tool | Build tool to detect paraphrased duplicates. Test on 20 known paraphrases. Calibrate threshold to 0.80 (95%+ recall, < 5% false positives). | Foundations |  | 1. Fuzzy matcher built and tested 2. 20 paraphrases: recall > 95%, FP < 5% 3. Threshold 0.80 documented 4. Tested on 10 known bespoke controls | Sprint 2 | Method: Jaccard similarity on word bigrams and trigrams. Implementation: from rapidfuzz import fuzz; similarity = fuzz.token_set_ratio(text1, text2) / 100. Calibration set: 20 control pairs (10 same-control-reworded, 10 different-controls). Tune threshold so recall > 95% and false positives < 5%. Test on 10 known bespoke controls from prior audit to verify real-world performance. File: 02_code/python/llm_orchestration/fuzzy_matcher.py.
Story | Find payment processes (deterministic paths) | Run PP1 (hierarchy), PP2 (value stream), PP3 (application), PP5 (keyword) on all Holocentric processes. Record paths fired per process. | Build the populations |  | 1. Four deterministic paths execute on full Holocentric 2. Payment process register with paths fired 3. Every process logged (include/exclude with reason) 4. Count by primary path | Sprint 2 | PP1: l2_process_name in ('Payments Processing', 'Fraud Management') OR l3_activity_name contains 'payment'. PP2: value_stream_name in ('Request to Payment', 'Fraud Detect to Correct'). PP3: applications field contains payment-relevant app ID. PP5: regex on lowcase(l3_activity_name ¦¦ ' ' ¦¦ l3_activity_description) matching '/payment¦payor¦payee¦settlement¦clearing¦bpay¦npp¦becs/'. Output: 03_data/intermediate/step02_payment_process_register.sas7bdat with pp1_fired, pp2_fired, pp3_fired, pp5_fired flags, primary_path, confidence_rollup (High if 2+ paths with 1+ being PP1/PP2, Medium if 1 path PP1/PP2/PP3, Low if only PP5). Audit: 05_audit_trail/audit_trail_step02_deterministic.csv.
Story | Find payment controls (deterministic paths) | Run P1 (taxonomy 7.4.x), P3 (obligation), P4 (incident/issue), P5 (keyword) on all JUNO controls. Record paths fired. | Build the populations |  | 1. Four deterministic paths on full JUNO 2. Payment control register with paths fired 3. Taxonomy hygiene finding (% non-P1) 4. Every control logged with decision | Sprint 2 | P1: risk_library_id like '7.4.%'. P3: ctrl_id in (select ctrl_id from linkage_ctrl_oblig where obligation_source in ('NPP', 'BECS', 'RBA', 'ePayments Code', 'AUSTRAC')). P4: ctrl_id in (select ctrl_id from linkage_ctrl_incident union select ctrl_id from linkage_ctrl_issue). P5: regex on lowcase(ctrl_description) matching payment terms. Output: 03_data/intermediate/step04_payment_control_register.sas7bdat with p1_fired, p3_fired, p4_fired, p5_fired, primary_path, confidence_rollup. Taxonomy hygiene: what % found via paths other than P1 (if > 40%, taxonomy tagging needs cleanup). Audit: 05_audit_trail/audit_trail_step04_deterministic.csv.
Story | Thin-slice demo (5 controls end-to-end) | Pick 5 real controls. Trace through steps 4, 8, 10, 11a manually. Produce one-page output for Sprint 2 demo. | Validation and audit |  | 1. Five controls selected (different Natures/CTs) 2. Each traced through 4 steps manually 3. One-page output showing data flow 4. Demo material ready | Sprint 2 | Select 5 controls: 1 automated preventative, 1 manual detective, 1 Requires Improvement rating, 1 bespoke candidate, 1 High-confidence taxonomy. For each: (1) show how included in step 4, (2) show CT mapping from step 8, (3) show bridge row from step 10, (4) show in heatmap cell from step 11a. Output format: one Excel tab per control showing journey. Demo to sponsor: proves pipeline works end-to-end before scaling.
Story | Find payment processes (embedding method PP6) | Compute embeddings for all processes. Find high-confidence core. Compare others via cosine similarity. Queue candidates to SME review. | Build the populations |  | 1. Embeddings for all Holocentric processes 2. High-confidence core identified 3. Similarity threshold calibrated using golden set 4. Candidates queued to SME (not auto-included) | Sprint 3 | Load embeddings from 04_embeddings/holocentric_process_embeddings.npy. High-confidence core: processes with pp1_fired=1 OR pp2_fired=1 OR pp3_fired=1. Compute cosine similarity of all other processes to core (average similarity to top-k nearest neighbors in core, k=10). Threshold calibration: use golden set from validation story, tune to achieve target precision/recall. Candidates above threshold go to 06_sme_review/step02_pp6_queue.xlsx, not auto-included. Avoids false positives from pure embedding method.
Story | Find payment controls (embedding method P6) | Compute embeddings for all controls. Compare to high-confidence core. Add enrichment signals (owner clustering, process-adjacency). Queue to SME. | Build the populations |  | 1. Embeddings for all JUNO controls 2. Similarity to core computed 3. Enrichment signals scored (owner, process-adjacency) 4. Candidates queued ordered by total score | Sprint 3 | Load embeddings from 04_embeddings/control_embeddings.npy. High-confidence core: controls with p1_fired=1 OR p3_fired=1. Compute similarity to core. Enrichment signals: (1) Owner clustering: if 80%+ of a business unit's controls are included, flag the rest, (2) Process-adjacency: controls on same application as included controls. Combined score: 0.5*similarity + 0.3*owner_clustering + 0.2*process_adjacency. Queue to 06_sme_review/step04_p6_queue.xlsx ordered by score descending.
Story | Run the convergence loop | Iterate steps 2 and 4. Step 2 fires PP4 (linked to High-confidence control). Step 4 fires P2 (linked to High-confidence process). Repeat until stable. | Build the populations |  | 1. Loop runs until no new High/Medium items 2. Confidence ceiling enforced (Medium cannot create High) 3. Low-confidence doesn't propagate 4. Pass-by-pass delta log | Sprint 3 | Pass 1: Steps 2 and 4 run with PP4/P2 disabled. Pass 2+: Step 2 fires PP4 (process linked to High-confidence control via linkage_ctrl_proc), Step 4 fires P2 (control linked to High-confidence process). Confidence propagation rules: (1) Only High/Medium items fire PP4/P2, (2) Medium source cannot create High inherited (ceiling), (3) Low items stay in SME queue. Convergence: when pass N and pass N+1 yield identical counts of High/Medium items. Hard cap: 5 passes. Output: 03_data/intermediate/convergence_log.csv showing pass_number, new_processes_added, new_controls_added per pass.
Story | Classify Payment Nature for processes | LLM classifies which of 5 Payment Natures apply to each process. Multi-nature allowed. Low-confidence to SME queue. | Classification |  | 1. LLM runs on all payment processes 2. Output: process-to-nature mapping with confidence/rationale 3. Low-confidence and multi-nature queued to SME 4. Validation gate passes before scaling | Sprint 3 | Prompt: 01_prompts/step03_payment_nature_processes.txt. Input per process: process_id, process_name, process_description (concatenated steps), value_stream, applications_used. Output JSON: applicable_natures array with {nature, confidence, rationale} per nature. Five natures: C to C (High risk), I to C (High), C to I (Medium), I to I (Medium), Supplier/Employee (Low). LLM can assign multiple natures if process spans multiple flows. Queue to SME: any with confidence=Low OR multiple natures with conflicting risk levels. Audit: 05_audit_trail/audit_trail_step03.csv. Validation: must pass golden set before scaling to full population.
Story | Build golden set for process inclusion (step 2) | SME labels 30 processes (10 clear-in, 10 clear-out, 10 edge). Independent LLM verifies. Measure primary model against SME labels. | Validation and audit |  | 1. SME constructs 30-process reference set 2. Independent LLM verifies SME labels 3. Primary model measured vs SME reference 4. Pass if false-negative rate < 10% | Sprint 3 | SME selects: 10 clear payment processes (BPAY processing, NPP settlements), 10 clear non-payment (HR onboarding, marketing campaigns), 10 edge cases (fraud monitoring touches payments but is it a payment process?). SME labels each: is_payment_process=True/False with rationale. Independent LLM (Gemini) verifies SME labels; disagreements adjudicated by SME. Primary model (Claude) runs on same 30, compare to SME reference. Metric: false-negative rate = (processes SME said True but model said False) / (total SME True). Pass if FNR < 10%. If fail, revise prompt and re-test. File: 06_sme_review/step02_golden_set.xlsx.
Story | Find bespoke controls in Holocentric steps | LLM checks each step in payment processes: does this step describe a control function? Fuzzy-match hits against JUNO. Unmatched = bespoke. | Build the populations |  | 1. LLM classifies all steps in payment processes 2. Positive results fuzzy-matched against JUNO 3. Unmatched written to bespoke register (source: Holocentric-step) 4. Audit trail per step | Sprint 4 | For each process in payment process register, extract all step descriptions. LLM prompt: Does this step perform a control function (approval, validation, reconciliation, monitoring, segregation, authorization)? JSON output: {is_control: true/false, control_description: extracted text, confidence}. Positive results (is_control=true): fuzzy-match control_description against all JUNO ctrl_description fields. If fuzzy similarity < 0.75, add to bespoke register: {bespoke_id, source_type='Holocentric-step', source_process_id, control_description, confidence}. Audit: 05_audit_trail/audit_trail_step05a.csv.
Story | Find bespoke controls in ALEX configs | If ALEX available: LLM checks config items for control functions (dual auth, thresholds, role segregation). Cross-check against JUNO automated controls. | Build the populations |  | 1. If ALEX: LLM classifies config items 2. Cross-checked against JUNO automated controls 3. Unmatched written to bespoke register (source: ALEX-config) 4. If ALEX unavailable: skip and document deferral | Sprint 4 | If ALEX coverage >= 20%: Extract config items and enforcement rules from ALEX for payment-relevant apps. LLM prompt: Does this config perform a control function (dual authorization, threshold enforcement, role segregation, approval workflows)? JSON: {is_control, control_description, confidence}. Cross-check against JUNO controls WHERE automation_level='Automated' AND application_id matches. Fuzzy-match descriptions. Unmatched = bespoke. If ALEX < 20%: create flag file 03_data/staging/step5b_deferred.flag, skip stream. File: 03_data/intermediate/step05_bespoke_register.sas7bdat with source_type field.
Story | Find bespoke controls in incident remediation text | LLM scans incident/issue closure text for control statements. Fuzzy-match against JUNO. Unmatched = bespoke. | Build the populations |  | 1. LLM extracts control statements from incident/issue text 2. Each extracted control fuzzy-matched against JUNO 3. Unmatched written to bespoke register (source: remediation) 4. Deduplicate within bespoke register | Sprint 4 | Query payment-related incidents/issues: WHERE ctrl_id in payment control register OR incident_summary contains payment terms. Extract closure_text, action_taken_text. LLM prompt: Extract any control statements from this text (new checks added, approvals introduced, monitoring established after failure). JSON: {controls_extracted: [{control_description, confidence}]}. For each extracted control: fuzzy-match against JUNO. Unmatched to bespoke register. After all three streams (5a, 5b, 5c): deduplicate within bespoke register itself (fuzzy-match within register, merge near-duplicates).
Story | Build golden set for bespoke discovery (step 5) | SME labels 40 items (20 Holocentric steps, 10 ALEX configs, 10 remediation texts). Measure precision (OK to miss some, prioritize low FP). | Validation and audit |  | 1. SME constructs 40-item reference set across 3 streams 2. Independent LLM verifies 3. Primary model measured vs SME reference 4. Pass if precision > 75% for all streams | Sprint 4 | SME selects: 20 Holocentric steps (10 are controls like 'supervisor approves batch', 10 are not like 'send email notification'), 10 ALEX configs (5 control, 5 not), 10 remediation texts (5 contain control statements, 5 don't). SME labels: is_control=True/False with rationale. Independent LLM verifies. Primary model runs on same 40. Metric: precision = (model said True AND SME said True) / (all model said True). Target precision > 75% per stream (OK to miss real controls, but low false-positive rate critical to avoid polluting bespoke register). File: 06_sme_review/step05_golden_set.xlsx.
Story | Assign Payment Nature to controls (inheritance) | For controls linked to processes: inherit Payment Natures from processes (UNION if multiple). Deterministic, High-confidence. | Classification |  | 1. Controls linked to processes inherit Natures (UNION) 2. Confidence = High (deterministic) 3. Output: control-to-nature mapping 4. Coverage: expect 60-80% of controls have process links | Sprint 5 | Join controls to processes via linkage_ctrl_proc table. For each control: Payment_Nature = UNION of all Payment_Natures from linked processes. Confidence = High (structural inheritance). SQL: SELECT c.ctrl_id, p.payment_nature FROM step04_payment_control_register c INNER JOIN linkage_ctrl_proc lnk ON c.ctrl_id=lnk.ctrl_id INNER JOIN step02_payment_process_register p ON lnk.bus_unit_bcrm_id=p.l3_activity_id. Handle multi-nature: control can have multiple natures if linked to processes with different natures. Output: 03_data/intermediate/step07_control_to_nature_inherited.sas7bdat. Coverage metric: what % of controls have process links (expect 60-80%; unlinked fall to LLM).
Story | Assign Payment Nature to controls (LLM fallback) | For controls without process links: LLM classifies Nature from control description. Confidence capped at Medium. All go to SME queue. | Classification |  | 1. LLM classifies unlinked controls 2. Confidence capped at Medium (no process link = less certain) 3. Output appended to control-to-nature mapping 4. All unlinked assignments queued to SME | Sprint 5 | Filter controls WHERE ctrl_id NOT IN (step 7 inherited). LLM prompt: Classify Payment Nature from control description and context (obligation text, incident text if available). Input: ctrl_id, ctrl_description, obligation_text, incident_summary. Output JSON: {applicable_natures: [{nature, confidence, rationale}]}. Confidence ceiling: even if LLM says High, cap at Medium (structural uncertainty from no process link). Append to 03_data/intermediate/step07_control_to_nature_all.sas7bdat. Queue all to 06_sme_review/step07_unlinked_queue.xlsx for SME review.
Story | Sanity check inherited Payment Natures | Sample 10% of controls with inherited Nature. LLM classifies them blind. Compare LLM vs inherited. If disagreement > 15%, re-validate step 3. | Classification |  | 1. Sample 10% controls with inherited Nature 2. LLM classifies sample blind 3. Disagreement rate measured 4. Pass if disagreement < 15%; if > 15%, halt and re-validate step 3 | Sprint 5 | Stratified sample: 10% of controls with inherited Payment Nature, stratified by nature, control_type, business_unit. LLM classifies sample (same prompt as step 7b fallback) WITHOUT seeing inherited result. Compare: disagreement = cases where LLM primary nature differs from inherited primary nature. Disagreement rate = disagreements / sample_size. Pass if < 15%. If >= 15%: indicates either (1) process linkages are incorrect, or (2) step 3 process classifications are wrong. Halt and re-validate step 3 golden set. Output: 03_data/intermediate/step07_sanity_check_results.csv.
Story | Build golden set for Payment Nature on processes (step 3) | SME labels 30 processes: 10 single-nature, 10 multi-nature, 10 ambiguous. Measure precision and recall per nature. | Validation and audit |  | 1. SME constructs 30-process reference set 2. Independent LLM verifies 3. Primary model measured per nature 4. Pass if all 5 natures meet precision > 85% AND recall > 80% | Sprint 5 | SME selects: 10 single-nature (clear C to C only, clear I to C only), 10 multi-nature (process spans C to C AND C to I), 10 ambiguous (borderline between natures). SME labels: applicable_natures per process with rationale. Independent LLM verifies. Primary model runs on same 30. Metrics computed per nature: Precision = (model said Nature X AND SME said Nature X) / (all model said Nature X). Recall = (model said Nature X AND SME said Nature X) / (all SME said Nature X). Pass if ALL five natures meet precision > 85% AND recall > 80%. File: 06_sme_review/step03_golden_set.xlsx.
Story | Map controls to Master Controls (CT1-CT28) | LLM maps each control to 1+ CTs. Also classifies category, nature, framework. Every CT assignment must cite control description phrase. | Classification |  | 1. LLM runs on all controls with CT mapping prompt 2. Output: control-to-CT mapping with cited rationale 3. Rationale grounding enforced (no citations = rejected) 4. Low-confidence and Governance-flagged queued to SME | Sprint 6 | Prompt: 01_prompts/step08_ct_mapping.txt. Input per control: ctrl_id, ctrl_description, control_type, automation_level. Output JSON: {ct_outcomes: [{ct: 'CT1', rationale_quote: 'phrase from description justifying CT1'}, ...], control_category: 'Process¦System¦Third-Party¦Pervasive', control_nature: 'Preventative¦Detective¦Corrective', framework_alignment: 'Payments¦Governance'}. Rationale grounding: response must cite specific phrases from ctrl_description. No citations = API call fails, retry. Queue to SME: confidence=Low OR framework_alignment='Governance' AND taxonomy_tag='7.4.x' (misclassified). Audit: 05_audit_trail/audit_trail_step08.csv. Biggest LLM workload: 3000-6000 API calls.
Story | Place controls in lifecycle stages | LLM assigns lifecycle stage A-G per control. Where possible, derive structural-expected stage from Holocentric step labels. Compare LLM vs structural. | Classification |  | 1. Structural placement derived where Holocentric step labels exist 2. LLM places all controls at lifecycle stage 3. Compare LLM to structural; disagreements flagged as misplacement candidates 4. Misplacement only possible where structural exists | Sprint 6 | Structural placement: For controls linked to Holocentric steps, parse step labels (common patterns: 'Initiate', 'Authorize', 'Post', 'Reconcile', 'Report'). Map to stages: A=Initiation, B=Validation, C=Authorization, D=Transmission/Execution, E=Posting, F=Reporting, G=Returns. Expect 30-60% of controls have structural signal. LLM places all controls (can combine with step 8 CT mapping in single prompt): lifecycle_stage: 'A¦B¦C¦D¦E¦F¦G'. Compare: where both structural and LLM exist, if they differ: flag as potential misplacement (control in wrong lifecycle stage). Output: 03_data/intermediate/step09_lifecycle_placement.sas7bdat with structural_stage, llm_stage, misplacement_flag fields.
Story | Build the bridge table | Join everything: controls, processes, CTs, Natures, lifecycle, linkages, ratings, incidents. Index on 5 dimensions. Every step 11 output queries this. | Bridge table |  | 1. Bridge table built from all upstream outputs 2. Indexes on 5 dimensions (CT, Nature, Stage, Category, Value Stream) 3. Row count reconciliation correct 4. Schema documented | Sprint 6 | SQL: SELECT c.ctrl_id, c.ctrl_name, c.control_category, c.automation_level, c.overall_effectiveness, ct.ct_outcome, n.payment_nature, lc.lifecycle_stage, p.l3_activity_id AS process_id, p.process_name, p.value_stream, lnk.linkage_type, inc.incident_count, inc.severity_max FROM step04_payment_control_register c LEFT JOIN step08_ct_mapping ct ON c.ctrl_id=ct.ctrl_id LEFT JOIN step07_control_to_nature_all n ON c.ctrl_id=n.ctrl_id LEFT JOIN step09_lifecycle_placement lc ON c.ctrl_id=lc.ctrl_id LEFT JOIN linkage_ctrl_proc lnk ON c.ctrl_id=lnk.ctrl_id LEFT JOIN step02_payment_process_register p ON lnk.bus_unit_bcrm_id=p.l3_activity_id LEFT JOIN incidents_summary inc ON c.ctrl_id=inc.ctrl_id. Create indexes: CREATE INDEX idx_ct ON bridge_table(ct_outcome); CREATE INDEX idx_nature ON bridge_table(payment_nature); etc. Reconciliation: sum(CTs per control * Natures per control) should equal bridge row count. Schema: 00_documentation/bridge_table_schema.xlsx.
Story | Build Requires Human Review queue | Create queue for Low-confidence LLM results and primary/independent disagreements. Prioritize by Nature risk + CT criticality. | Validation and audit |  | 1. Queue table schema with source step, item, results, disagreement type 2. All LLM steps populate queue when Low or disagree 3. Queue queryable by filters 4. SME resolution workflow: review, decide, record rationale, propagate | Sprint 6 | Queue table: item_id, source_step (2/3/5/7/8/9), item_description, primary_result, independent_result, disagreement_type (Low-confidence¦Disagreement), nature_risk (High¦Medium¦Low), ct_criticality (P0¦P1¦P2), priority_score (computed), assigned_sme, status (Pending¦Reviewed), sme_decision (Approve Primary¦Approve Independent¦Revise Custom¦Reject), sme_rationale, resolution_date. Populate from all LLM steps: if confidence=Low OR primary != independent, INSERT INTO queue. Priority score: (nature_risk weight * 3) + (ct_criticality weight * 2). SME workflow: Excel interface 06_sme_review/sme_queue_combined.xlsx with dropdowns and comments. Resolution propagates via 02_code/python/queue_resolver.py updating source datasets.
Story | Build golden set for CT mapping (step 8) | SME labels 50 controls covering all 28 CTs. Measure CT-level precision and recall. | Validation and audit |  | 1. SME constructs 50-control reference set stratified by CT, automation, source 2. SME assigns CTs with grounded rationale 3. Independent LLM verifies 4. Pass if avg precision > 85% AND avg recall > 80% across 28 CTs | Sprint 6 | Stratified sample: 50 controls ensuring every CT appears at least once (some CTs have 3-4 controls, rare CTs have 1). Mix: automated/manual, key control/non-key, JUNO/bespoke. SME assigns: ct_outcomes per control (1-N CTs) with rationale grounded in ctrl_description citing specific phrases. Independent LLM verifies SME labels. Primary model runs on same 50. Metrics per CT: Precision(CTx) = (model assigned CTx AND SME assigned CTx) / (model assigned CTx). Recall(CTx) = same numerator / (SME assigned CTx). Pass if average across all 28 CTs: precision > 85% AND recall > 80%. File: 06_sme_review/step08_golden_set.xlsx.
Story | Build golden set for lifecycle placement (step 9) | Reuse 50 controls from step 8. SME adds lifecycle stage. Measure exact-match accuracy. | Validation and audit |  | 1. Reuse 50 controls from step 8 golden set 2. SME adds lifecycle stage with rationale 3. Independent LLM verifies 4. Pass if exact-match accuracy > 80% (40+ correct) | Sprint 6 | Reuse same 50 controls from step 8 (already stratified). SME adds: lifecycle_stage (A-G) with rationale (why this stage not others). Independent LLM verifies. Primary model runs on same 50. Metric: exact-match accuracy = (model assigned correct stage) / 50. Pass if >= 40 out of 50 correct (80%). Easier metric than step 8 because only 7 choices not 28, and stage often obvious from description (reconciliation = E, authorization = C). File: 06_sme_review/step09_golden_set.xlsx.
Story | Produce coverage heatmaps (three cuts) | Query bridge table: Nature by CT, Value Stream by CT, Process by CT. Each cell: Structural, Effective, Failing counts. Export to Excel with color coding. | Analytical outputs |  | 1. Nature by CT heatmap (5x28) 2. Value Stream by CT heatmap (8-12x28) 3. Process by CT heatmap (200-500x28) 4. Excel with conditional formatting (green/amber/red) | Sprint 7 | SQL per heatmap: SELECT payment_nature, ct_outcome, SUM(CASE WHEN ctrl_id IS NOT NULL THEN 1 ELSE 0 END) AS structural_coverage, SUM(CASE WHEN overall_effectiveness IN ('Effective', 'Largely Effective') THEN 1 ELSE 0 END) AS effective_coverage, SUM(CASE WHEN overall_effectiveness IN ('Effective', 'Largely Effective') AND incident_count > 0 THEN 1 ELSE 0 END) AS failing_coverage FROM bridge_table GROUP BY payment_nature, ct_outcome. Repeat for value_stream and process_id. Excel export with 3 tabs. Conditional formatting: GREEN if Effective > 3 AND Failing = 0, AMBER if Effective 1-2 OR Failing > 0, RED if Structural = 0. File: 03_data/outputs/11a_coverage_heatmaps.xlsx.
Story | Produce strengthen view | Query bridge for strong controls: automated in High-risk Natures, preventative at early stages, Effective with zero incidents (exemplars). | Analytical outputs |  | 1. Automated controls in High-risk natures 2. Preventative controls at critical stages (A, B, C) 3. Exemplar candidates (Effective + no incidents 24mo) 4. Output consolidated with subset type flag | Sprint 7 | Three queries: (1) WHERE automation_level='Automated' AND payment_nature IN ('C to C', 'I to C'). (2) WHERE control_nature='Preventative' AND lifecycle_stage IN ('A', 'B', 'C'). (3) WHERE overall_effectiveness IN ('Effective', 'Largely Effective') AND incident_count_24mo = 0. UNION ALL three with subset_type field ('Automated-HighRisk', 'Preventative-Early', 'Exemplar'). Export to 03_data/outputs/11b_strengthen_view.xlsx with tabs per subset.
Story | Produce governance controls misclassified report | Find controls WHERE framework='Governance' AND taxonomy='7.4.x'. These should be removed from Payments and re-homed under Governance Risk. | Analytical outputs |  | 1. Filter: framework='Governance' AND taxonomy='7.4.x' (expect 30-100) 2. Include rationale from step 8 explaining Governance classification 3. Output: ctrl_id, name, owner, current tag, rationale, recommendation 4. Export to Excel for risk owner review | Sprint 7 | SQL: SELECT c.ctrl_id, c.ctrl_name, c.ctrl_description, c.owner_business_unit, c.risk_library_id AS current_tag, ct.framework_alignment, ct.framework_rationale FROM bridge_table b INNER JOIN step08_ct_mapping ct ON b.ctrl_id=ct.ctrl_id WHERE ct.framework_alignment='Governance' AND c.risk_library_id LIKE '7.4.%'. Add column: recommendation='Remove from 7.4.x Payments Risk, re-home under Governance Risk framework'. Export to 03_data/outputs/11d_governance_misclassified.xlsx. Example: controls about committee oversight, policy authorship, training delivery.
Story | Produce obligations coverage view | For each Payments obligation: list controls covering it. Derive coverage rating: Strong (3+ Effective), Moderate (1-2), Weak (only Req Improvement), None (0). Flag gaps. | Analytical outputs |  | 1. Per obligation: join to controls, aggregate counts 2. Coverage rating (Strong/Moderate/Weak/None) 3. Regulatory gaps (None or Weak) with priority by regulator 4. Export to Excel | Sprint 7 | SQL: SELECT o.obligation_id, o.obligation_text, o.obligation_source (NPP, BECS, RBA), COUNT(DISTINCT c.ctrl_id) AS total_controls, SUM(CASE WHEN c.overall_effectiveness IN ('Effective', 'Largely Effective') THEN 1 ELSE 0 END) AS effective_controls FROM obligations o LEFT JOIN linkage_ctrl_oblig lnk ON o.obligation_id=lnk.obligation_id LEFT JOIN bridge_table c ON lnk.ctrl_id=c.ctrl_id GROUP BY o.obligation_id. Derive rating: Strong if effective_controls >= 3, Moderate if 1-2, Weak if total_controls > 0 AND effective_controls = 0, None if total_controls = 0. Regulatory gaps: WHERE rating IN ('None', 'Weak') ORDER BY obligation_source priority (NPP=P0, RBA=P0, BECS=P1). Export to 03_data/outputs/11f_obligations_coverage.xlsx.
Story | Track inter-model agreement over time | After each LLM run: compute agreement rate (primary vs independent). If < 70%, trigger re-validation alert. Track drift over time. | Validation and audit |  | 1. Agreement rate computed per step run 2. If < 70%, append alert to log 3. Dashboard: track agreement rate over time 4. Line chart per step, 70% threshold marked | Sprint 7 | After each LLM step production run: compare primary model result to independent model result. Agreement = (both models give same answer) / (total items). Per step: step02_agreement, step03_agreement, etc. Alert logic: IF agreement < 0.70 THEN append to 05_audit_trail/validation_alerts.log ('Step X agreement dropped to Y% on date Z - investigate prompt drift, model updates, data quality'). Dashboard: Power BI or Excel line chart, X-axis=run_date, Y-axis=agreement_rate, separate line per step, horizontal line at 70% threshold. Detects model drift.
Story | Build mechanism similarity calculator | Build tool to compute mechanism similarity between two controls. Combines embeddings + automation + control type. Used in Sprint 8 for duplicates. | Analytical outputs |  | 1. Function: compute_mechanism_similarity(control_A, control_B) returns 0-1 2. Uses embeddings + automation + type encoding 3. Tested on known duplicates (> 0.90) and non-duplicates (< 0.70) 4. Code documented with examples | Sprint 7 | Python function (02_code/python/llm_orchestration/mechanism_similarity.py): def compute_mechanism_similarity(ctrl_A, ctrl_B, embeddings_dict): (1) Get description embeddings for both (3072-dim), (2) Encode automation_level as one-hot: Automated=[1,0,0], Hybrid=[0,1,0], Manual=[0,0,1], (3) Encode control_type: Preventative=[1,0,0], Detective=[0,1,0], Corrective=[0,0,1], (4) Concatenate: combined_A = [embedding_A, auto_A, type_A] (3078-dim), (5) Cosine similarity. CRITICAL RULE: if automation differs, NOT duplicate even if similarity >= 0.75 (defense-in-depth). Test cases: (1) Same control reworded: expect > 0.90, (2) Automated vs manual for same CT: expect < 0.70 due to automation difference.
Story | Produce duplicate clusters and best-of-breed | Find duplicates: same CT/Nature/Stage/Process with mechanism similarity > 0.75. Within clusters, score on 5 factors. Highest = best-of-breed. | Analytical outputs |  | 1. Cluster by (CT, Nature, Stage, Process) with similarity > 0.75 2. Score: 40% effectiveness, 25% automation, 20% incident-free, 10% design clarity, 5% coverage breadth 3. Rank within cluster, highest = best-of-breed 4. Output per cluster: all controls with scores, retire/merge rec | Sprint 8 | Step 1: Pre-cluster by (ct_outcome, payment_nature, lifecycle_stage, process_scope). Step 2: Within each pre-cluster, compute pairwise mechanism similarity (call mechanism_similarity.py). If similarity >= 0.75 AND automation_level matches, controls are duplicates. Step 3: Score each control: 0.40 * effectiveness_score (Effective=3, Largely=2, Req Impr=1, Ineffective=0, Unverified=0) + 0.25 * automation_score (Automated=3, Hybrid=2, Manual=1) + 0.20 * incident_free_score (no incidents 24mo=1, else=0) + 0.10 * design_clarity_score (description length > 50 words AND readability=1, else=0.5) + 0.05 * coverage_breadth_score (linked to 3+ processes=1, else=0). Step 4: Within each cluster, rank by total score. Highest = best-of-breed. Output: 03_data/outputs/11c_duplicates_best_of_breed.xlsx with cluster_id, controls in cluster, scores, best-of-breed flag, recommendation (retire/merge others into best-of-breed).
Story | Produce gap register (six types) | Detect 6 gap types: A (no coverage), B (insufficient rating), C (unverified), D (failing), E (misplacement), F (process gap). Rank by priority. | Analytical outputs |  | 1. Six gap types extracted with specific queries per type 2. Priority: P0 = High-risk nature + P0 CT, P1 = High + P1 OR Medium + P0, P2 = rest 3. Consolidated gap register 4. Export to Excel | Sprint 8 | Type A (no coverage): Generate all (Nature x CT) combos, left join to bridge, WHERE control_count=0. Type B (insufficient): GROUP BY (Nature, CT), HAVING all controls rated Req Improvement or Ineffective. Type C (unverified): WHERE overall_effectiveness IS NULL. Type D (failing): WHERE overall_effectiveness IN ('Effective', 'Largely Effective') AND incident_count > 0 in 12mo. Type E (misplacement): WHERE structural_stage != llm_stage. Type F (process gap): processes with no linked controls. UNION ALL six types with gap_type field. Priority: CASE WHEN nature_risk='High' AND ct_criticality='P0' THEN 'P0' WHEN (nature_risk='High' AND ct_criticality='P1') OR (nature_risk='Medium' AND ct_criticality='P0') THEN 'P1' ELSE 'P2' END. Export to 03_data/outputs/11e_gap_register_consolidated.xlsx with tab per gap type.
Story | Produce JUNO registration backlog | Extract bespoke controls confirmed by SMEs. Enrich with CT/Nature/Stage. Rank by priority. This is post-PoC JUNO registration to-do list. | Analytical outputs |  | 1. Filter bespoke controls to SME-confirmed=TRUE 2. Enrich with CT, Nature, Stage, linked processes/apps 3. Priority ranking (same as gap register) 4. Output: full schema with source, description, owner, priority | Sprint 8 | SQL: SELECT b.bespoke_id, b.source_type (Holocentric-step, ALEX-config, remediation), b.control_description, b.source_process_id, ct.ct_outcome, n.payment_nature, lc.lifecycle_stage, p.applications, sme.sme_decision FROM step05_bespoke_register b LEFT JOIN sme_queue_resolution sme ON b.bespoke_id=sme.item_id WHERE sme.sme_decision IN ('Approve Primary', 'Approve Independent', 'Revise Custom') /* only SME-confirmed */ LEFT JOIN step08_ct_mapping ct ON b.bespoke_id=ct.ctrl_id LEFT JOIN step07_control_to_nature_all n ON b.bespoke_id=n.ctrl_id LEFT JOIN step09_lifecycle_placement lc ON b.bespoke_id=lc.ctrl_id LEFT JOIN step02_payment_process_register p ON b.source_process_id=p.l3_activity_id. Add priority_rank (same logic as gap register). Recommended registration owner: inherit from source_process owner. Export to 03_data/outputs/11g_juno_registration_backlog.xlsx.
Story | Produce monitoring baseline | Per CT: identify key controls (top by best-of-breed score), recommend monitoring intensity (Low/Medium/High/Critical), list evidence vs gaps. | Analytical outputs |  | 1. Key controls per CT (top 3-5 by score) 2. Monitoring intensity (Critical/High/Medium/Low) based on risk + incidents 3. Existing evidence (assessments, KRIs, monitoring) 4. Gaps flagged (evidence=0 or stale > 12mo) | Sprint 8 | Per CT: Query bridge ORDER BY best_of_breed_score DESC LIMIT 5 to get key controls. Monitoring intensity per CT: CASE WHEN nature_risk='High' AND incident_count_24mo > 5 THEN 'Critical' WHEN nature_risk='High' OR incident_count_24mo > 2 THEN 'High' WHEN nature_risk='Medium' THEN 'Medium' ELSE 'Low' END. Existing evidence: join to internal monitoring log (assessments, KRIs, automated monitoring) via ctrl_id, check latest_assessment_date. Gaps: WHERE monitoring_evidence=0 OR latest_assessment_date < CURRENT_DATE - 365. Export to 03_data/outputs/11h_monitoring_baseline.xlsx with tab per CT showing key controls, intensity, evidence, gaps.
Story | PoC retrospective and reusability handover | Document what's reusable (12-step structure, bridge architecture, validation framework) vs Payments-specific (CT1-28, Natures, stages). Estimate effort for second risk class. | Validation and audit |  | 1. Backbone vs overlay documented (generic method vs Payments taxonomies) 2. Effort estimate for second risk class (20-30% faster) 3. Lessons learned (what worked, what needs improvement) 4. Handover document for future PoCs | Sprint 9 | Reusable backbone: (1) 12-step methodology structure, (2) Deterministic + embedding + LLM convergence pattern, (3) Bridge table architecture (process, control, outcome, nature, stage), (4) Validation framework (golden sets, SME queues, independent LLM cross-check, audit trail), (5) Confidence rollup formulas, (6) Gap detection taxonomy. Payments-specific overlay: (1) CT1-CT28 definitions, (2) 5 Payment Natures, (3) Lifecycle stages A-G, (4) Payment-specific keywords/value streams. Effort for second risk class (e.g., Operational Risk, Credit Risk): expect 20-30% faster because backbone is proven; only need to define new outcome taxonomy and nature taxonomy. Lessons learned: what prompts worked well, what validation gates caught issues, where SME time was bottleneck, where LLM struggled. Output: 00_documentation/reusability_handover.docx.