## Backlog
Issue Type | Summary | Description | Epic Link | Epic Name | Acceptance Criteria | Sprint
Epic | Foundations | Set up the environment, load data, and build the tools you'll use throughout the PoC. This includes getting JUNO, Holocentric, and ALEX data into SAS, setting up LLM access, building the prompt library, and creating the audit trail framework. |  | Foundations
Epic | Build the populations | Find all the payment processes and payment controls. Use multiple methods (taxonomy tags, value streams, keywords, embeddings) to make sure you catch everything, then let them converge until the lists stabilize. |  | Build the populations
Epic | Classification | Classify everything using LLMs: which Payment Natures apply to each process, which Payment Natures apply to each control, which Master Controls (CT1-CT28) each control delivers, and which lifecycle stage (A-G) each control operates at. |  | Classification
Epic | Bridge table | Combine everything from the previous steps into one master table. Every row is a unique combination of process, control, CT outcome, Payment Nature, and lifecycle stage. All the outputs in step 11 query this table. |  | Bridge table
Epic | Analytical outputs | Produce the findings: coverage heatmaps, gap register, duplicate controls, JUNO registration backlog, obligations coverage, and monitoring recommendations. These are what you show the sponsor. |  | Analytical outputs
Epic | Validation and audit | Make sure the LLM work is accurate. SMEs build golden sets and review Low-confidence cases. An independent LLM cross-checks the primary model. Disagreements go to SMEs for adjudication. Full audit trail captured for every AI decision. |  | Validation and audit
Story | Get LLM access working | Make sure you can call two different LLM models (like Claude and Gemini) from your SAS/Python environment. Test that they return structured JSON. Store credentials securely. | Foundations |  | 1. Can successfully call two different LLM model families 2. Test prompt returns valid JSON from both models 3. Credentials stored securely (no hardcoded API keys) 4. Rate limiting and retry logic implemented | Sprint 1
Story | Check what's in JUNO | Load JUNO controls into SAS and run basic checks. Count how many are tagged Payments (7.4.x), how many have effectiveness ratings, and whether linkage tables have broken references. This tells you if you have what you need. | Foundations |  | 1. JUNO data loaded to SAS staging 2. Count: total controls, Payments-tagged (7.4.x), controls with ratings, controls with process links 3. Check for orphan keys in linkage tables (count should be under 5%) 4. Simple summary table produced with go/no-go decision | Sprint 1
Story | Check what's in Holocentric | Load Holocentric processes into SAS and check data quality. Count processes, check how many have descriptions (needed for LLM work), and verify they link to JUNO controls via the linkage table. | Foundations |  | 1. Holocentric data loaded to SAS staging 2. Count: L2 processes, L3 activities, processes with descriptions (need over 80%) 3. Check: how many Holocentric processes link to JUNO controls (expect 40-70%) 4. Simple summary table with go/no-go decision | Sprint 1
Story | Check linkage tables and obligations | Load the four linkage tables (Control to Process, Obligation, Incident, Issue) and the underlying datasets. Count how many controls have links, what severities incidents have, and which regulations obligations come from. | Foundations |  | 1. All four linkage tables loaded to SAS 2. Count: controls with process links, controls with obligation links, controls with incidents/issues 3. Profile: incident severity distribution (P1/P2/P3), obligation sources (NPP, BECS, RBA, etc.) 4. Verify join keys work end-to-end | Sprint 1
Story | Check what's in ALEX and Alfabet | Load ALEX and Alfabet extracts. ALEX links controls to applications and shows CDEs (Critical Data Elements). Alfabet is the application master list. Check coverage: how many JUNO controls appear in ALEX, how many applications are payment-relevant. If ALEX is missing or poor quality, flag it early. | Foundations |  | 1. ALEX and Alfabet data loaded to SAS 2. Count: how many JUNO controls appear in ALEX (expect 40-80%) 3. Extract payment-relevant application list (apps used by payment processes) 4. If ALEX missing or low coverage, document impact on step 5b (bespoke discovery stream) | Sprint 1
Story | Build the schema dictionary | Combine all the data checks into one Excel file listing every field from every source. Include data type, null rate, example values, and which steps use each field. This is your reference for the whole PoC. | Foundations |  | 1. Schema dictionary Excel file created covering all sources: JUNO, Holocentric, ALEX, Alfabet, linkages 2. Each field documented: name, data type, null rate, example values, which steps use it 3. Data quality findings documented (high null rates, orphan keys, missing sources) 4. Lead engineer sign-off before Sprint 2 starts | Sprint 1
Story | Onboard SMEs and brief them | Identify 2-3 SMEs from Line 1 Risk and Compliance. Brief them on their role: build golden sets for validation, review Low-confidence cases, adjudicate disagreements. Confirm they can commit 2-4 hours/week in Sprints 1-3, 4-8 hours/week in Sprints 4-8. | Validation and audit |  | 1. 2-3 SMEs identified and onboarded (names, roles, availability documented) 2. Briefing session completed (PoC objectives, validation approach, golden set process, review queue workflow) 3. SMEs commit to time: 2-4 hours/week Sprints 1-3, 4-8 hours/week Sprints 4-8 4. Primary SME and backup designated | Sprint 1
Story | Build the prompt library | Write the initial LLM prompts for all six LLM-driven steps (steps 2, 3, 5, 7, 8, 9). Each prompt needs: instructions, input shape, JSON output schema, confidence rubric. Store prompts in version control with SHA hash tracking for audit trail. | Foundations |  | 1. Prompts written for steps 2, 3, 5a/b/c, 7b/c, 8, 9 and saved to prompts folder 2. Each prompt has clear JSON output schema documented 3. Prompt versioning: SHA hash computed and tracked per prompt file 4. Any prompt change triggers re-validation flag | Sprint 2
Story | Build the audit trail framework | Create the system that logs every LLM decision: prompt version, model ID, timestamp, input hash, raw response, parsed result. This lets you reproduce any decision later and proves the work is auditable. | Foundations |  | 1. Audit trail table schema created with required fields: prompt hash, model ID, timestamp, input hash, response 2. Test: single LLM call writes complete audit record 3. Re-run test: given audit record, reproduce exact same LLM call 4. All LLM scripts include audit logging function | Sprint 2
Story | Set up embedding infrastructure | Choose an embedding model (recommend text-embedding-3-large or ada-002). Test it on 100 processes and 100 controls. Build a batch processor that handles rate limits and saves embeddings to numpy files. Needed for steps 2, 4, and 11c. | Foundations |  | 1. Embedding model selected and tested on sample (100 processes, 100 controls) 2. Batch processor built with rate limiting and retry logic 3. Embeddings saved to efficient format (numpy .npy files with CSV index) 4. End-to-end test: 200 items processed in under 30 seconds | Sprint 2
Story | Build fuzzy matching tool | Build a tool that compares text descriptions to detect duplicates (needed for step 5 bespoke discovery). Test on 20 paraphrased control descriptions. Calibrate threshold: at 0.80 similarity you should catch 95%+ of paraphrases with under 5% false positives. | Foundations |  | 1. Fuzzy matcher built (recommend Jaccard similarity on word bigrams and trigrams) 2. Tested on 20 paraphrased controls: recall over 95%, false positives under 5% 3. Threshold 0.80 selected and documented in config file 4. Tested on 10 known bespoke controls to verify real-world performance | Sprint 2
Story | Find payment processes (deterministic paths) | Run four methods to find payment processes in Holocentric: hierarchy (sits under Payments L2), value stream (Request to Payment, Fraud Detect to Correct), application (uses payment apps), keyword (description contains payment terms). Record which paths fired for each process. | Build the populations |  | 1. Four deterministic paths execute on full Holocentric universe (hierarchy, value stream, application, keyword) 2. Output: payment process register with paths fired per process 3. Every Holocentric process logged (included or excluded) with reason 4. Count processes by primary path (tells you which method is most effective) | Sprint 2
Story | Find payment controls (deterministic paths) | Run four methods to find payment controls in JUNO: taxonomy tag (7.4.x), obligation linkage (NPP, BECS, RBA), incident/issue linkage, keyword (description contains payment terms). Record which paths fired for each control. | Build the populations |  | 1. Four deterministic paths execute on full JUNO universe (taxonomy, obligation, incident/issue, keyword) 2. Output: payment control register with paths fired per control 3. Taxonomy hygiene finding: what % of controls found via non-taxonomy paths (if over 40%, taxonomy needs fixing) 4. Every JUNO control logged with reason for include/exclude decision | Sprint 2
Story | Thin-slice demo (5 controls end-to-end) | Pick 5 real controls. Run them through steps 4 (find control), 8 (map to CTs), 10 (add to bridge), 11a (show in heatmap). Produce one-page output showing each control's journey. Use this for Sprint 2 sponsor demo to prove the pipeline works. | Validation and audit |  | 1. Five controls selected covering different Payment Natures and control types 2. Each control traced through four steps manually (inclusion, CT mapping, bridge, heatmap) 3. One-page output produced showing data flow for all 5 controls 4. Sponsor demo material ready (proves end-to-end pipeline works before scaling) | Sprint 2
Story | Find payment processes (embedding method) | Compute embeddings for all Holocentric processes. Find the high-confidence core (processes already included via deterministic paths). Compare other processes to this core using cosine similarity. Processes above threshold go to SME queue for review (not auto-included). | Build the populations |  | 1. Embeddings computed for all Holocentric processes 2. High-confidence core identified (processes from hierarchy/value stream/application paths) 3. Similarity threshold calibrated using golden set from validation story 4. Candidate processes queued to SME review (not auto-included) | Sprint 3
Story | Find payment controls (embedding method) | Compute embeddings for all JUNO controls. Find high-confidence core (controls already included). Compare other controls to core. Add enrichment signals: owner clustering (if 80%+ of a business unit's controls are included, flag the rest), process-adjacency (controls on same system as included controls). Queue candidates to SME review. | Build the populations |  | 1. Embeddings computed for all JUNO controls 2. Similarity to high-confidence core computed 3. Enrichment signals scored (owner clustering, process-adjacency) to prioritize SME queue 4. Candidates queued to SME review ordered by total score | Sprint 3
Story | Run the convergence loop | Run steps 2 and 4 alternately. Step 2 fires path PP4 (process linked to High-confidence control). Step 4 fires path P2 (control linked to High-confidence process). Keep iterating until both lists stop growing. Only High-confidence items propagate; Low-confidence stays in SME queue. | Build the populations |  | 1. Convergence loop runs steps 2 and 4 alternately until stable (no new High/Medium items added) 2. Confidence ceiling enforced: Medium-confidence source cannot create High-confidence inherited item 3. Low-confidence items do not propagate (stay in SME queue) 4. Pass-by-pass delta log shows how populations grew (expect convergence in 2-3 passes) | Sprint 3
Story | Classify Payment Nature for processes | For each payment process, LLM classifies which Payment Natures apply (Customer to Customer, Institution to Customer, etc.). A process can have multiple natures. Output includes confidence and rationale per nature. Low-confidence cases go to SME queue. | Classification |  | 1. LLM runs on all payment processes with Payment Nature classification prompt 2. Output: process-to-nature mapping with confidence and rationale per nature 3. Low-confidence and multi-nature edge cases queued to SME 4. Validation gate from golden set must pass before scaling to full population | Sprint 3
Story | Build golden set for process inclusion (step 2) | SME selects 30 Holocentric processes: 10 clear payment processes, 10 clear non-payment, 10 edge cases. SME labels each (is this a payment process yes/no). Independent LLM verifies. Primary model measured against SME labels. Target: false-negative rate under 10%. | Validation and audit |  | 1. SME constructs 30-process reference set (clear-in, clear-out, edge cases) 2. Independent LLM verifies SME labels (disagreements adjudicated by SME) 3. Primary model run on same 30 processes and measured against SME reference 4. Pass if false-negative rate under 10%; iterate prompt if not | Sprint 3
Story | Find bespoke controls in Holocentric steps | For each payment process, LLM checks every step description to see if it describes a control function (approval, validation, reconciliation, etc.). Positive results are fuzzy-matched against JUNO. Unmatched items are candidate bespoke controls (controls operating in practice but not registered in JUNO). | Build the populations |  | 1. LLM classifies all steps in payment processes (is this step a control function yes/no) 2. Positive results fuzzy-matched against JUNO controls for same process 3. Unmatched items written to bespoke control register with source type Holocentric-step 4. Audit trail captured per step classification | Sprint 4
Story | Find bespoke controls in ALEX configs | If ALEX data is available: LLM checks config items and enforcement rules to see if they perform control functions (dual authorization, threshold enforcement, role segregation, etc.). Cross-check against JUNO automated controls for same application. Unmatched items are candidate bespoke controls. | Build the populations |  | 1. If ALEX available: LLM classifies config items (is this a control yes/no) 2. Positive results cross-checked against JUNO automated controls for same application 3. Unmatched items written to bespoke register with source type ALEX-config 4. If ALEX unavailable: skip and document deferral | Sprint 4
Story | Find bespoke controls in incident remediation text | LLM scans incident and issue closure text to find control-like statements (new checks added, approvals introduced, monitoring established after a failure). Fuzzy-match each extracted control against JUNO. Unmatched items are candidate bespoke controls. | Build the populations |  | 1. LLM extracts control statements from payment incident/issue remediation text 2. Each extracted control fuzzy-matched against full JUNO universe 3. Unmatched items written to bespoke register with source type remediation 4. After all three bespoke streams complete, deduplicate within bespoke register itself | Sprint 4
Story | Build golden set for bespoke discovery (step 5) | SME labels 40 items: 20 Holocentric steps (10 that are controls, 10 that are not), 10 ALEX configs, 10 remediation texts. Independent LLM verifies. Primary model measured. Target: precision over 75% (OK to miss some bespoke controls; prioritize low false-positive rate). | Validation and audit |  | 1. SME constructs 40-item reference set across three bespoke streams (Holocentric, ALEX, remediation) 2. Independent LLM verifies SME labels 3. Primary model measured against SME reference 4. Pass if precision over 75% for all three streams; iterate prompts if not | Sprint 4
Story | Assign Payment Nature to controls (inheritance) | For controls linked to processes, inherit the Payment Natures from those processes (take the UNION if linked to multiple processes). This is deterministic and High-confidence. Controls with no process link get NULL here and fall back to LLM classification. | Classification |  | 1. Join controls to processes via linkage table, inherit Payment Natures (UNION of all linked processes) 2. Confidence set to High (deterministic inheritance) 3. Output: control-to-nature mapping for controls with process links 4. Count coverage: expect 60-80% of controls have process links | Sprint 5
Story | Assign Payment Nature to controls (LLM fallback) | For controls with no process link, LLM classifies Payment Nature directly from control description and context (obligation text, incident text if available). Confidence capped at Medium (no process link means less certain). All unlinked assignments go to SME queue. | Classification |  | 1. LLM classifies Payment Nature for controls with no process link (20-40% of population) 2. Confidence capped at Medium even if LLM is confident (structural uncertainty) 3. Output appended to control-to-nature mapping 4. All unlinked assignments queued to SME for review | Sprint 5
Story | Sanity check inherited Payment Natures | Take a 10% sample of controls with inherited Payment Nature. LLM classifies them directly (blind to inherited result). Compare LLM vs inherited. If disagreement rate over 15%, it means either process linkages are wrong or step 3 process classifications are wrong. Triggers re-validation of step 3. | Classification |  | 1. Sample 10% of controls with inherited Payment Nature (stratified by nature, control type, business unit) 2. LLM classifies sample directly, compare to inherited assignment 3. Disagreement rate measured (count where LLM differs from inherited, divided by sample size) 4. Pass if disagreement under 15%; if over 15%, halt and re-validate step 3 | Sprint 5
Story | Build golden set for Payment Nature on processes (step 3) | SME selects 30 processes: 10 single-nature, 10 multi-nature, 10 ambiguous. SME labels applicable natures per process. Independent LLM verifies. Primary model measured. Target: precision over 85% and recall over 80% per nature. | Validation and audit |  | 1. SME constructs 30-process reference set covering single/multi/ambiguous nature assignments 2. Independent LLM verifies SME labels 3. Primary model measured per nature (precision and recall computed separately for each of five natures) 4. Pass if all five natures meet precision over 85% AND recall over 80% | Sprint 5
Story | Map controls to Master Controls (CT1-CT28) | LLM maps each control to one or more Master Control outcomes (CT1-CT28). Also classifies control category (Process/System/Third-Party/Pervasive), control nature (Preventative/Detective/Corrective), and framework alignment (Payments vs Governance). Every CT assignment must cite the control description phrase that justifies it. This is the biggest LLM workload (3000-6000 API calls). | Classification |  | 1. LLM runs on all controls (JUNO plus bespoke) with CT mapping prompt 2. Output: control-to-CT mapping with rationale citing control description, plus category/nature/framework fields 3. Rationale grounding enforced: responses without source text citations are rejected 4. Low-confidence cases and Governance-flagged controls queued to SME | Sprint 6
Story | Place controls in lifecycle stages | LLM assigns each control to a payment lifecycle stage (A Initiation through G Returns and Recoveries). Where possible, derive structural-expected stage from Holocentric step labels. Compare LLM placement to structural expectation. Disagreements are potential misplacement findings. | Classification |  | 1. Structural placement derived where Holocentric step labels exist (expect 30-60% coverage) 2. LLM places all controls at lifecycle stage (can combine with step 8 CT mapping in single prompt) 3. Compare LLM to structural where both exist; disagreements flagged as misplacement candidates 4. Misplacement detection only possible where structural-expected exists | Sprint 6
Story | Build the bridge table | Join everything together into one master table. Each row is a unique combination of process, control, CT outcome, Payment Nature, and lifecycle stage. Index on the five key dimensions for fast queries. Every output in step 11 queries this table. | Bridge table |  | 1. Bridge table built by joining: controls, processes, CT mappings, Payment Natures, lifecycle stages, linkages, ratings, incidents/issues 2. Indexes created on five dimensions (CT, Payment Nature, lifecycle, category, value stream) 3. Row count reconciliation: total bridge rows equal sum of (CTs per control times Natures per control) 4. Schema documented with every column source and join key | Sprint 6
Story | Build Requires Human Review queue | Create a persistent queue of items needing SME review. Populated by: Low-confidence LLM results and disagreements between primary and independent LLMs. Queue prioritized by Payment Nature risk plus CT criticality. SMEs work this queue throughout the PoC. | Validation and audit |  | 1. Queue table schema created with fields: source step, item ID, primary result, independent result, disagreement type, confidence, timestamp 2. All LLM steps populate queue when confidence is Low or primary/independent disagree 3. Queue queryable by filters (step, disagreement type, priority, assigned SME) 4. SME resolution workflow: review item, decide (approve/revise/reject), record rationale, propagate back to source datasets | Sprint 6
Story | Build golden set for CT mapping (step 8) | SME selects 50 controls covering all 28 CTs, mix of automated/manual, JUNO/bespoke. SME assigns CT outcomes per control with rationale. Independent LLM verifies. Primary model measured. Target: CT-level precision over 85% and recall over 80%. | Validation and audit |  | 1. SME constructs 50-control reference set stratified by CT, automation, key control flag, source type 2. SME assigns CT outcomes per control (1-N CTs) with rationale grounded in description 3. Independent LLM verifies SME labels 4. Pass if average precision over 85% AND average recall over 80% across all 28 CTs | Sprint 6
Story | Build golden set for lifecycle placement (step 9) | Reuse the same 50 controls from step 8 golden set. SME assigns lifecycle stage per control. Independent LLM verifies. Primary model measured. Target: exact-match accuracy over 80% (40+ out of 50 correct). | Validation and audit |  | 1. Reuse 50 controls from step 8 golden set (already selected and stratified) 2. SME adds lifecycle stage assignment per control with rationale 3. Independent LLM verifies SME labels 4. Pass if exact-match accuracy over 80% (LLM assigns correct stage for 40+ controls) | Sprint 6
Story | Produce coverage heatmaps (three cuts) | Query the bridge table to build three heatmaps: Payment Nature by CT, Value Stream by CT, Process by CT. Each cell shows three numbers: Structural coverage (control exists), Effective coverage (control rated Effective), Failing coverage (rated Effective but has incidents). Export to Excel with color coding. | Analytical outputs |  | 1. Payment Nature by CT heatmap (5 rows, 28 columns, three numbers per cell) 2. Value Stream by CT heatmap (8-12 rows, 28 columns) 3. Process by CT heatmap (200-500 rows, 28 columns) 4. Excel export with conditional formatting: green if Effective over 3 and Failing equals 0, amber if Effective 1-2 or Failing over 0, red if Structural equals 0 | Sprint 7
Story | Produce strengthen view | Query bridge table to highlight strong controls: automated controls in High-risk Payment Natures, preventative controls at early lifecycle stages (Initiation, Validation, Authorization), and Effective controls with zero incidents in 24 months (candidate exemplars). | Analytical outputs |  | 1. Automated controls in High-risk natures (Customer to Customer, Institution to Customer) extracted 2. Preventative controls at critical stages (A, B, C) extracted 3. Exemplar candidates: Effective rating plus no incidents in 24 months 4. Output consolidated with subset type flag, exported to Excel | Sprint 7
Story | Produce governance controls misclassified report | Find controls flagged Governance (addresses policy/committee/training) but tagged 7.4.x Payments in JUNO. These should be removed from Payments Risk framework and re-homed under Governance Risk. Include rationale from step 8 explaining why each reads as governance. | Analytical outputs |  | 1. Filter: framework alignment equals Governance AND JUNO taxonomy tag 7.4.x (expect 30-100 controls) 2. Include rationale from step 8 explaining Governance classification 3. Output format: control ID, name, description, owner, current tag, rationale, recommendation to de-scope 4. Export to Excel for risk owner review | Sprint 7
Story | Produce obligations coverage view | For each Payments obligation (NPP, BECS, RBA, ePayments Code, AUSTRAC), list the controls covering it. Derive coverage rating per obligation: Strong (3+ Effective controls), Moderate (1-2 Effective), Weak (only Requires Improvement controls), None (zero controls). Flag obligations with None or Weak coverage as regulatory gaps. | Analytical outputs |  | 1. For each payment obligation, join to controls via linkage table 2. Aggregate per obligation: count total controls, count Effective controls 3. Derive coverage rating (Strong/Moderate/Weak/None) 4. Extract regulatory gap findings (None or Weak coverage) with priority by regulator | Sprint 7
Story | Track inter-model agreement over time | After each LLM production run, independent LLM re-runs the same items. Compute agreement rate (percent where both models give same answer). If agreement drops below 70%, trigger re-validation alert. Track over time to detect drift. | Validation and audit |  | 1. Agreement rate computed after each LLM step run (primary vs independent results) 2. If agreement below 70%, append alert to log (check prompt changes, model updates, data quality) 3. Dashboard updated: track agreement rate over time per step 4. Line chart shows drift: one line per step, 70% threshold marked | Sprint 7
Story | Produce duplicate clusters and best-of-breed | Find duplicate controls: controls sharing same CT outcome, Payment Nature, lifecycle stage, and process scope, with mechanism similarity over 0.75. Within each cluster, score controls on five factors (effectiveness, automation, incident-free history, design clarity, coverage breadth). Highest score is best-of-breed; others are retire/merge candidates. | Analytical outputs |  | 1. Cluster controls by (CT, Nature, Stage, Process Scope) with mechanism similarity over 0.75 2. Score each control: 40% effectiveness, 25% automation, 20% incident-free, 10% design clarity, 5% coverage breadth 3. Within each cluster: rank by score, highest is best-of-breed 4. Output per cluster: all controls with scores, best-of-breed flag, retire/merge recommendation | Sprint 8
Story | Produce gap register (six types) | Identify six gap types: A (no coverage), B (rated insufficient), C (unverified), D (failing despite Strong rating), E (misplacement), F (process gap). Rank gaps by Payment Nature inherent risk plus CT criticality (P0/P1/P2). Consolidate into single gap register. | Analytical outputs |  | 1. Six gap types extracted: A no coverage, B insufficient rating, C unverified, D failing, E misplacement, F process gap 2. Each gap type measured against bridge table or source datasets 3. Priority ranking applied: P0 equals High-risk nature plus P0 CT, P1 equals High-risk plus P1 CT or Medium plus P0 CT, P2 equals all others 4. Consolidated gap register exported with gap type, affected entity, priority, recommended action | Sprint 8
Story | Produce JUNO registration backlog | Extract bespoke controls that SMEs confirmed as genuine (not false positives from LLM discovery). Rank by Payment Nature risk plus CT criticality. This is the to-do list for registering controls in JUNO post-PoC. | Analytical outputs |  | 1. Filter bespoke controls to SME-confirmed equals TRUE only 2. Enrich with CT mappings, Payment Natures, lifecycle stages, linked processes/applications 3. Priority ranking applied (same as gap register) 4. Output: full schema with source type, description, recommended registration owner, priority | Sprint 8
Story | Produce monitoring baseline | For each Master Control (CT1-CT28): identify key controls (top-ranked by best-of-breed score), recommend monitoring intensity (Low/Medium/High/Critical based on inherent risk and incident history), list existing monitoring evidence vs gaps. | Analytical outputs |  | 1. Key controls per CT identified (top 3-5 by best-of-breed score or effectiveness plus incident-free) 2. Monitoring intensity scored per CT (Critical if High-risk plus recurring incidents, High if High-risk or recurring incidents, Medium if Medium-risk, Low if Low-risk stable) 3. Existing evidence identified (recent assessments, KRIs, automated monitoring) 4. Gaps flagged where monitoring evidence equals zero or stale over 12 months | Sprint 8
Story | PoC retrospective and reusability handover | Document what's reusable (the 12-step structure, bridge table architecture, validation framework) vs what's Payments-specific (CT1-CT28, Payment Natures, lifecycle stages). Estimate effort to apply this method to a second risk class. Consolidate lessons learned from all sprints. | Validation and audit |  | 1. Backbone vs overlay documented: generic 12-step method vs Payments-specific taxonomies 2. Effort estimate for second risk class (expect 20-30% faster due to reusable backbone) 3. Lessons learned consolidated: what worked, what needs improvement, what to do differently 4. Handover document finalized with recommendations for future PoCs in other risk domains | Sprint 9